Karnataka State Commission for Women (KSCW)

Complaint Management System (CMS)

Module & Feature-wise Effort Estimate

Client Copy · Effort in person-hours

This estimate covers software feature implementation effort for the KSCW Complaint Management System (web and mobile), based on the agreed Statement of Work. Hours are person-hours for design-aligned build of the listed capabilities.

Hours do not include infrastructure procurement, SMS/email gateway commercial charges, CERT-In Safe-to-Host auditor fees beyond contractual inclusion, classroom training delivery logistics, physical digitization, or the 3-year warranty operations commercial envelope (quoted separately as lump-sum warranty under the IFQ).

1. Summary Totals

| Item | Hours |
| --- | --- |
| Recommended go-live (Modules 01–07) | 1012 |
| Optional / later enhancements (baseline) | 0 |
| All estimated feature hours | 1012 |

2. Module-wise Summary

| # | Module | Type | Features | Hours | % of go-live |
| --- | --- | --- | --- | --- | --- |
| 01 | User Access & Role Management | Shared | 4 | 114 | 11.3% |
| 02 | Master Data & System Configuration | Shared | 5 | 135 | 13.3% |
| 03 | Multi-Channel Complaint Registration | Business | 6 | 192 | 19.0% |
| 04 | Categorization, Auto-Routing & Assignment | Business | 4 | 127 | 12.5% |
| 05 | Workflow Automation, Escalation & SLA Tracking | Business | 5 | 176 | 17.4% |
| 06 | Notifications & Alerts (SMS / Email) | Technical | 3 | 103 | 10.2% |
| 07 | Dashboards, Analytics, Real-time Monitoring & MIS | Business | 4 | 165 | 16.3% |
|  | Total |  | 31 | 1012 | 100% |

3. Feature-wise Estimate

01. User Access & Role Management (114 hours)

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F01-001 | User Lifecycle Management | 26 | Create, update, activate / deactivate CMS users |
| F01-002 | Role & Permission Assignment | 34 | Configure Admin, Supervisor, Operator and FRS-defined roles |
| F01-003 | Authentication & Session Control | 32 | Secure login and session handling for web and mobile |
| F01-004 | Access Audit | 22 | Record privileged user/role changes for audit |

02. Master Data & System Configuration (135 hours)

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F02-001 | Complaint Taxonomy Masters | 26 | Categories, sub-categories, departments, priorities |
| F02-002 | Location / Jurisdiction Masters | 28 | Location hierarchy for routing and reporting |
| F02-003 | SLA & Escalation Configuration | 39 | SLA timers and escalation matrix parameters |
| F02-004 | Notification Templates | 24 | SMS/Email templates and trigger mapping |
| F02-005 | Status & Parameter Configuration | 18 | Complaint statuses and system parameters |

03. Multi-Channel Complaint Registration (192 hours)

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F03-001 | Web Complaint Registration | 39 | Complaint intake on web |
| F03-002 | Mobile Complaint Registration | 37 | Complaint intake on mobile application |
| F03-003 | Email Channel Intake | 44 | Register / ingest email-originated complaints |
| F03-004 | Call-Center Intake | 24 | Operator registration of call-center complaints |
| F03-005 | Complaint Acknowledgement | 20 | Unique reference and acknowledgement |
| F03-006 | Attachment / Evidence Capture | 28 | Upload and link supporting documents/media |

04. Categorization, Auto-Routing & Assignment (127 hours)

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F04-001 | Complaint Categorization | 22 | Apply / update category and related classification |
| F04-002 | Auto-Routing Engine | 41 | Route by department, priority, location rules |
| F04-003 | Worklist & Assignment | 38 | Supervisor / Operator queues and assignment |
| F04-004 | Reassignment / Reclassification | 26 | Controlled transfer with history |

05. Workflow Automation, Escalation & SLA Tracking (176 hours)

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F05-001 | Workflow Stage Processing | 45 | Action complaints through configured stages |
| F05-002 | Escalation Matrix Execution | 28 | Auto / manual escalation per configured matrix |
| F05-003 | SLA Tracking & Aging | 41 | SLA timers, breaches, and aging views |
| F05-004 | Resolution & Closure | 28 | Close / resolve with reasons and evidence |
| F05-005 | Supervisor Oversight | 34 | Monitor pending, escalated, and breached items |

06. Notifications & Alerts (SMS / Email) (103 hours)

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F06-001 | SMS Notification Dispatch | 40 | SMS alerts for configured complaint events |
| F06-002 | Email Notification Dispatch | 32 | Email alerts for configured complaint events |
| F06-003 | Notification Log & Retry Support | 31 | Delivery status tracking and operational retry |

07. Dashboards, Analytics, Real-time Monitoring & MIS (165 hours)

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F07-001 | Operational Dashboards | 39 | Role-based operational dashboard views |
| F07-002 | Real-time Monitoring | 46 | Near-real-time intake, pending, SLA, escalations |
| F07-003 | Analytics Views | 41 | Analytical summaries per approved design |
| F07-004 | MIS Reports & Export | 39 | Standard MIS reports with export |

4. Effort Profile

| Type | Hours | % |
| --- | --- | --- |
| Business | 660 | 65.2% |
| Shared | 249 | 24.6% |
| Technical / Integrations | 103 | 10.2% |

Highest-effort features (indicative):

• F07-002 — Real-time Monitoring (46 h) · Dashboards, Analytics, Real-time Monitoring & MIS

• F05-001 — Workflow Stage Processing (45 h) · Workflow Automation, Escalation & SLA Tracking

• F03-003 — Email Channel Intake (44 h) · Multi-Channel Complaint Registration

• F07-003 — Analytics Views (41 h) · Dashboards, Analytics, Real-time Monitoring & MIS

• F05-003 — SLA Tracking & Aging (41 h) · Workflow Automation, Escalation & SLA Tracking

• F04-002 — Auto-Routing Engine (41 h) · Categorization, Auto-Routing & Assignment

• F06-001 — SMS Notification Dispatch (40 h) · Notifications & Alerts (SMS / Email)

• F07-004 — MIS Reports & Export (39 h) · Dashboards, Analytics, Real-time Monitoring & MIS

5. Indicative Delivery Phasing

Per the IFQ / SOW, software delivery is planned within one (1) month from supply order (working-day milestones through commissioning), followed by a three (3) year warranty period. Feature hours above support the application build; warranty services are contractual sustainment and are not added into the feature-hour total.

6. Not Included in Feature Hours

• Server / storage / network hardware (provided by KSCW)

• SMS and email gateway recurring commercial charges

• CERT-In empaneled auditor engagement logistics beyond IFQ inclusion

• Classroom training venue/logistics; video production studio costs if any

• Data cleansing ownership (KSCW); physical scanning of paper archives

• 3-year warranty helpdesk/uptime/redeployment commercial envelope (IFQ lump-sum warranty)

• Major scope added after FRS approval (change request)

7. Key Planning Assumptions

1. Final field-level scope is locked by approved FRS, UI/UX & Workflow Design, and Dashboard Design.

2. Access model is User → Role → Permissions (Admin, Supervisor, Operator + FRS roles).

3. Web and mobile applications are in scope; email and call-center intake as defined in FRS.

4. Infrastructure is provided by KSCW; agency provides requirement documents and deploys on that infrastructure.

5. SMS/Email gateway credentials and access are facilitated by KSCW / KEONICS.

6. Estimates assume enterprise-grade validation, security, logging, and test coverage for listed features.

7. One-month calendar is a contractual delivery window; staffing intensity must match the hour volume.

Disclaimer: Figures are indicative person-hour estimates for planning and commercial discussion. They are not a fixed-price bid unless expressly adopted in a commercial proposal / purchase order.