FOOD, CIVIL SUPPLIES & CONSUMER AFFAIRS DEPARTMENT

Government of Karnataka

Client Copy · Effort in person-hours

Module & Feature-wise Effort Estimate

FCS Karnataka State Command and Control Centre

# 1. Purpose

This estimate sets out indicative person-hours to design, build, test and document FCS Karnataka State Command and Control Centre application software (CCC platform, integrations, dashboards, GIS views, CCTV analytics, alerts, incidents and MIS). It excludes CCC room hardware, field GPS/CCTV devices, KSDC consumption, AMC/O&M manpower and classroom training.

# 2. Summary totals

| Item | Person-hours |
| --- | --- |
| Recommended go-live | 3,392 |
| Optional / conditional | 0 |
| All-in (this baseline) | 3,392 |
| Features | 30 |
| Modules | 12 |

# 3. Module-wise summary

| Module | Type | Features | Hours | % of go-live |
| --- | --- | --- | --- | --- |
| 01. Person, Post, Role and Access Governance | Shared | 6 | 529 | 15.6% |
| 02. Organisation and Location Masters | Business | 2 | 178 | 5.2% |
| 03. Vehicle and GPS Device Onboarding | Business | 2 | 220 | 6.5% |
| 04. Route Master and Route Compliance | Business | 2 | 209 | 6.2% |
| 05. GPS Live Monitoring and Trip Lifecycle | Business | 2 | 302 | 8.9% |
| 06. RFID Vehicle Identification | Business | 2 | 216 | 6.4% |
| 07. ANPR Vehicle Detection | Business | 2 | 220 | 6.5% |
| 08. CCTV Surveillance Monitoring | Business | 3 | 416 | 12.3% |
| 09. Alerts, Incidents and Escalation | Business | 2 | 240 | 7.1% |
| 10. Command Control Dashboards and GIS | Business | 2 | 242 | 7.1% |
| 11. Reports, MIS and Analytics | Business | 2 | 182 | 5.4% |
| 12. External Integrations Hub | Technical | 3 | 438 | 12.9% |
| Total |  | 30 | 3,392 | 100% |

# 4. Feature-wise estimate

## 01. Person, Post, Role and Access Governance — 529 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F01-001 | Person Master | 87 | Foundational person directory. |
| F01-002 | Post Master and Organisational Placement | 87 | Unit-scoped post catalogue. |
| F01-003 | Post-to-Person Mapping with Effective Dates | 121 | Effective-dated occupancy. |
| F01-004 | Role-to-Post Mapping and Permission Matrix | 106 | Post-level permission matrix. |
| F01-005 | Authentication, Session and Optional 2FA | 79 | Login and Post selection. |
| F01-006 | Access Audit Log | 49 | Access forensic log. |

## 02. Organisation and Location Masters — 178 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F02-001 | District, Taluk and Administrative Unit Master | 81 | Admin geography catalogue. |
| F02-002 | Wholesale Godown and FPS Location Master | 97 | Warehouse and FPS locations for geo-fence and GIS. |

## 03. Vehicle and GPS Device Onboarding — 220 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F03-001 | Vehicle and Transporter Master | 95 | Vehicle/transporter catalogue. |
| F03-002 | GPS Device Onboarding and Health Monitoring | 125 | AIS-140 device mapping. |

## 04. Route Master and Route Compliance — 209 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F04-001 | Route Master, Geo-fence and Stoppage Configuration | 126 | Route and geo-fence catalogue. |
| F04-002 | Vehicle-to-Route Assignment and Compliance Rules | 83 | Assignment and compliance setup. |

## 05. GPS Live Monitoring and Trip Lifecycle — 302 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F05-001 | Live Vehicle Tracking Dashboard | 138 | State-wide live GPS view. |
| F05-002 | Trip Lifecycle, Replay and Utilization | 164 | Trip start/end, halt, replay. |

## 06. RFID Vehicle Identification — 216 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F06-001 | RFID Tag and Reader Master | 115 | RFID tag/reader catalogue. |
| F06-002 | RFID Entry Exit Detection and Compliance Log | 101 | Entry/exit and unauthorized detection. |

## 07. ANPR Vehicle Detection — 220 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F07-001 | ANPR Camera Registration and Site Mapping | 111 | ANPR camera catalogue. |
| F07-002 | ANPR Capture, Entry Exit Log and Unauthorized Detection | 109 | Plate capture and analytics. |

## 08. CCTV Surveillance Monitoring — 416 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F08-001 | CCTV Camera Onboarding and Health | 144 | Camera catalogue and health. |
| F08-002 | Live CCTV Monitoring and Playback | 116 | Live view and playback. |
| F08-003 | Video Analytics Rules and Events | 156 | Tripwire, intrusion, IMD events and escalation. |

## 09. Alerts, Incidents and Escalation — 240 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F09-001 | Alert Rules and Notification Dispatch | 117 | Alert engine. |
| F09-002 | Incident Register, Escalation and Closure | 123 | Incident management. |

## 10. Command Control Dashboards and GIS — 242 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F10-001 | Role-based Operational and Executive Dashboards | 140 | Unified CCC dashboards. |
| F10-002 | GIS Monitoring Map | 102 | GIS visualization. |

## 11. Reports, MIS and Analytics — 182 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F11-001 | Operational and Compliance Reports | 71 | Core MIS reports. |
| F11-002 | Analytical Dashboards KPIs and Scheduled Reports | 111 | Analytics and schedules. |

## 12. External Integrations Hub — 438 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F12-001 | VLTS and Multi-vendor GPS Integration | 142 | GPS/VLTS API integration. |
| F12-002 | CCTV ONVIF and Multi-vendor Video Integration | 130 | CCTV ecosystem integration. |
| F12-003 | SMART-PDS Vahan Sarathi and API Management | 166 | Departmental and RTO APIs. |

# 5. Items not included in feature hours

CCC room hardware (video wall, consoles, network, UPS) and civil works.

GPS device supply, SIM, vehicle installation and field GPS maintenance.

CCTV camera supply, installation, NVR/DVR and camera field networking (analytics engines on cameras remain with field ecosystem).

KSDC hosting consumption (INR).

AMC (2 years), O&M / resident manpower and classroom training.

# 6. Planning assumptions

Access is Person → Post → Role with unit-scoped data (State CCC / District / Godown).

VLTS, CCTV/ONVIF and analytics event interfaces will be available for integration; SMART-PDS / Vahan / Sarathi operations confirmed during design.

Video analytics covers CCC configuration, event intake, review and escalation for tripwire, intrusion and intelligent motion detection.

Document attachments are embedded in processes; no standalone DMS.

No bulk legacy CCC database migration is included in this baseline.

# 7. Disclaimer

These figures are indicative person-hours for planning and commercial discussion. They assume a production-quality build with validation, error handling, logging, security and unit testing.