KEONICS  ·  Department of Mines and Geology, Bengaluru Urban

Module & Feature-wise Effort Estimate

Scanning and Digitization of Files and Records

Client Copy  ·  Effort in person-hours (operational software)

Version 1.0  ·  September 2026

# 1. Purpose

This estimate sets out indicative person-hours to design, build, test and document the operational software that supports the KEONICS Invitation for Quotation for scanning and digitization at the Department of Mines and Geology, Bengaluru Urban (unique file identity, inward and outward logs, scan production recording, quality-check recording, metadata, e-Office upload, backup verification and progress reports). These hours do not replace the IFQ quotation lines for pre-scanning, scanning, post-scanning and metadata labour, nor the supply of scanners, computers and licensed imaging tools.

# 2. Summary totals

| Item | Person-hours |
| --- | --- |
| Recommended go-live (operational software) | 749 |
| Optional / conditional | 0 |
| All-in (this software baseline) | 749 |
| Features | 17 |
| Modules | 6 |

# 3. Module-wise summary

| Module | Type | Features | Hours | % of go-live |
| --- | --- | --- | --- | --- |
| 01. User and Access Management | Shared | 3 | 128 | 17.1% |
| 02. File Inward, Unique ID and Pre-Scan Control | Business | 3 | 141 | 18.8% |
| 03. Scanning and Searchable PDF/A Production | Business | 3 | 117 | 15.6% |
| 04. Quality Control and Physical Return | Business | 3 | 137 | 18.3% |
| 05. Metadata, Cataloguing and Indexing | Business | 2 | 93 | 12.4% |
| 06. e-Office Upload, Backup and Progress MIS | Technical | 3 | 133 | 17.8% |
| Total |  | 17 | 749 | 100% |

# 4. Feature-wise estimate

## 01. User and Access Management — 128 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F01-001 | Project Staff Accounts | 50 | Service Provider and Department users with name, designation and ID |
| F01-002 | Login and Role Session | 48 | Sign-in as Operator, Supervisor or Department Officer |
| F01-003 | Authorised Handover List | 30 | Who may hand over and receive physical files |

## 02. File Inward, Unique ID and Pre-Scan Control — 141 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F02-001 | Unique File ID | 40 | Unique ID marked on file covers and noting pages |
| F02-002 | Inward Log and Page Census | 61 | Inward log and page counts by size |
| F02-003 | Pre-Scan Batch and Exceptions | 40 | Batch preparation; missing page or unfit-for-scan flags |

## 03. Scanning and Searchable PDF/A Production — 117 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F03-001 | Scan Production Recording | 48 | Pages scanned by size and colour; blank pages excluded |
| F03-002 | Searchable PDF/A Package | 43 | One searchable PDF/A per physical file |
| F03-003 | Exception Capture Devices | 26 | Overhead, flatbed, camera or high-DPI capture |

## 04. Quality Control and Physical Return — 137 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F04-001 | Independent QC Checklist | 57 | Independent image-quality checklist |
| F04-002 | Rescan and Defect Closure | 36 | Failed quality checks tracked through rescan |
| F04-003 | Outward Log and Physical Return | 44 | Daily return of reconstituted files with countersignature |

## 05. Metadata, Cataloguing and Indexing — 93 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F05-001 | Folder Tree and File Naming | 38 | Department-approved folder path and file name |
| F05-002 | File Metadata Capture | 55 | Active, Closed and Archive quarry-lease metadata |

## 06. e-Office Upload, Backup and Progress MIS — 133 hours

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F06-001 | e-Office and Department Upload | 59 | e-Office or Department system upload with retry |
| F06-002 | Backup and Restore Verification | 34 | Daily backup log and restore tests |
| F06-003 | Progress Reports | 40 | Daily, weekly, monthly and overall progress |

# 5. Effort profile

| Type | Hours |
| --- | --- |
| Shared | 128 |
| Business | 488 |
| Technical | 133 |
| Total | 749 |

Largest features (indicative)

| Feature ID | Feature Name | Hours |
| --- | --- | --- |
| F02-002 | Inward Log and Page Census | 61 |
| F06-001 | e-Office and Department Upload | 59 |
| F04-001 | Independent QC Checklist | 57 |
| F05-002 | File Metadata Capture | 55 |
| F01-001 | Project Staff Accounts | 50 |
| F03-001 | Scan Production Recording | 48 |

# 6. Indicative delivery phasing

| Phase | Primary modules |
| --- | --- |
| Access and file custody | User access; unique ID; inward log |
| Scan, quality check and return | PDF/A production; independent QC; outward log |
| Catalogue, upload and MIS | Metadata; e-Office upload; backup; progress reports |

The IFQ contract period is two months of on-site scanning. The grouping above is for building the operational software, not a second commercial phase of the IFQ.

# 7. Items not included in feature hours

Pre-scanning, scanning (A4/Legal and A3 or larger), post-scanning and metadata labour at the IFQ indicative volumes (quote those five lines separately)

High-speed, overhead and flatbed scanners, computers, servers, LAN, UPS, printers, consumables and licensed quality-check imaging software

Office space, furniture, electricity and internet provided by the Department

Building or customising e-Office or a public or mobile application

SLA cash penalties, liquidated damages and GST bid evaluation

Payment for blank pages

# 8. Planning assumptions

1. Work is only at the office of the Senior Geologist, Department of Mines and Geology, Bengaluru Urban.

2. Files do not leave Department premises. Physical files are returned daily to authorised officers.

3. Access is Operator, Supervisor or Department Officer. There is no person or post directory.

4. Searchable PDF/A files must work with e-Office; a sample compatibility check is done before full-scale scanning.

5. Metadata follows Active, Closed and Archive quarry-lease fields and may be extended by the Department.

6. Feature hours cover the operational software only. The five IFQ quotation lines remain a commercial bid.

7. If e-Office allows only manual upload, upload recording still applies; a system-to-system feed may not be available.

8. Contract duration is two months; payment is after Department certification as in the IFQ.

# 9. Disclaimer

These figures are indicative person-hours for planning and commercial discussion of the operational software. They are not a quote for scanning page rates, a staffing plan for the two-month on-site team, or a calendar duration. The Invitation for Quotation remains the commercial baseline for service quantities and SLA.