Auction Management System

Module and Feature-wise Effort Estimate

Client copy · Effort in person-hours

# Purpose of this estimate

This estimate covers the effort to design, build, and verify the Auction Management System described in the Statement of Work: catalogue, auction creation and approval, publication, corrigendum, bidder participation, pre-live evaluation when the auction requires it, live bidding, monitoring and closure, ranking, finalisation, award, and Letter of Intent.

The hours are person-hours for application delivery. They include the business behaviour, the screens and operations that support it, data retention for those operations, verification, and operating notes. They do not include hosting, network infrastructure, payment collection, SMS, mobile applications, data migration, training workshops, or support after go-live.

# Summary

| Item | Person-hours |
| --- | --- |
| Recommended go-live | 2171 |
| Optional items | 0 |
| All-in total | 2171 |
| Modules | 15 |
| Features | 46 |

The go-live scope includes both auctions that evaluate bidders before the live session and auctions that do not. An auction that skips evaluation does not remove the need to build that path, because each auction chooses the path when it is created.

# Module summary

| Module | Type | Features | Hours | Share of go-live |
| --- | --- | --- | --- | --- |
| 01. Staff Access and Role Management | Shared | 4 | 165 | 7.6% |
| 02. Category and Catalogue Management | Business | 5 | 246 | 11.3% |
| 03. Bidder Registration and Profile | Business | 4 | 183 | 8.4% |
| 04. Auction Creation | Business | 6 | 275 | 12.7% |
| 05. Auction Review, Approval and Publication | Business | 2 | 104 | 4.8% |
| 06. Corrigendum Management | Business | 2 | 95 | 4.4% |
| 07. Auction Discovery and Participation | Business | 4 | 187 | 8.6% |
| 08. Pre-Auction Query and Clarification | Business | 1 | 59 | 2.7% |
| 09. Pre-Live Participation Evaluation | Business | 2 | 111 | 5.1% |
| 10. Live Auction Bidding and Extension | Business | 3 | 175 | 8.1% |
| 11. Live Auction Monitoring and Closure | Business | 3 | 107 | 4.9% |
| 12. Results, Finalisation and Approval | Business | 3 | 164 | 7.6% |
| 13. Award and Letter of Intent | Business | 3 | 129 | 5.9% |
| 14. Notifications | Technical | 2 | 90 | 4.1% |
| 15. Auction Status and History | Business | 2 | 81 | 3.7% |
| Total |  | 46 | 2171 | 100% |

# Feature detail

## 01. Staff Access and Role Management

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F01-001 | Staff User Accounts | 50 | Named staff accounts and active status for catalogue, auction, and award duties. |
| F01-002 | Role Assignment and Permissions | 57 | Assigns the seven staff roles and enforces them on later actions. |
| F01-003 | Department Master and Staff Department | 24 | Flat department list used on staff accounts, auctions, and bidder search. |
| F01-004 | Staff Login and Session | 34 | Staff sign-in, sign-out, and password reset. Separate from the bidder portal. |
|  | Module total | 165 |  |

## 02. Category and Catalogue Management

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F02-001 | Category and Sub-category Management | 57 | Category tree plus image, video, and location requirements. |
| F02-002 | Reusable Field Master | 34 | Reusable text, number, date, select, and boolean fields. |
| F02-003 | Field Options for Select Fields | 28 | Ordered, activatable options for select fields only. |
| F02-004 | Category–Field Mapping | 39 | Maps fields to a category with required flag and display order. |
| F02-005 | Catalogue Item Maintenance | 88 | Dynamic catalogue item with media, location, activation, and search. |
|  | Module total | 246 |  |

## 03. Bidder Registration and Profile

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F03-001 | Bidder Self-Registration | 43 | Bidder submits organisation and contact details and waits for verification. |
| F03-002 | Bidder Account Verification | 57 | Staff verifier activates or rejects a bidder before that bidder can participate. |
| F03-003 | Bidder Login and Session | 26 | Bidder portal sign-in, separate from staff sign-in. |
| F03-004 | Bidder Profile, Organisation and Documents | 57 | Bidder maintains organisation, contacts, and master documents. |
|  | Module total | 183 |  |

## 04. Auction Creation

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F04-001 | Auction Basic Information and Participation Rules | 53 | Draft header: direction, bid type, display flags, evaluation, and any closed bidder list. |
| F04-002 | Pricing, EMD and Bid Parameters | 41 | Item or lot structure, GST format, EMD type, bid-change price, and reserve amounts. |
| F04-003 | Catalogue Item Selection and Lot Organisation | 61 | Selects active catalogue items and arranges lots without editing the master. |
| F04-004 | Auction Supporting Documents | 30 | Uploads auction papers in the stated formats, up to 70 MB each. |
| F04-005 | Participation and Live Auction Schedule | 39 | Four schedule points, 15 or 30 minute delta, and next-day cutoff. |
| F04-006 | Draft Review and Submit for Approval | 51 | Creator reviews the full draft and submits it for approval. |
|  | Module total | 275 |  |

## 05. Auction Review, Approval and Publication

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F05-001 | Auction Review and Decision | 63 | Reviewer approves a submitted auction or sends it back with remarks. |
| F05-002 | Auction Notice and Publication | 41 | Assigns the auction notice number and publishes the approved auction. |
|  | Module total | 104 |  |

## 06. Corrigendum Management

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F06-001 | Corrigendum Draft and Approval | 61 | Drafts a numbered corrigendum and obtains approval before bidders see it. |
| F06-002 | Corrigendum Publication and Bidder Access | 34 | Publishes an approved corrigendum so eligible bidders can read it. |
|  | Module total | 95 |  |

## 07. Auction Discovery and Participation

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F07-001 | Published Auction Search and Detail | 53 | Bidder searches published auctions and reads the pack they are allowed to see. |
| F07-002 | Expression of Interest and Participation | 43 | Bidder participates in the window and confirms once EMD and documents are complete. |
| F07-003 | EMD Fulfilment | 47 | Records common, item-wise, or lot-wise EMD with reference and proof. No payment gateway. |
| F07-004 | Participation Document Upload | 44 | Bidder files the auction’s required participation documents for evaluation staff to read. |
|  | Module total | 187 |  |

## 08. Pre-Auction Query and Clarification

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F08-001 | Pre-auction Query and Clarification | 59 | Bidder asks, and the department posts a clarification on the auction before the deadline. |
|  | Module total | 59 |  |

## 09. Pre-Live Participation Evaluation

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F09-001 | Participation Evaluation and Eligibility Decision | 74 | Evaluator marks each confirmed participant accepted or rejected before the live auction. |
| F09-002 | Accepted Bidder List Approval | 37 | Approves the accepted-bidder list that gates the live auction. |
|  | Module total | 111 |  |

## 10. Live Auction Bidding and Extension

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F10-001 | Live Bid Submission | 84 | Eligible bidder submits item or lot bids in a forward or reverse live auction. |
| F10-002 | Live Bid Validation and Visibility | 56 | Accepts or rejects a live bid against direction, change, time, and eligibility, and applies display masks. |
| F10-003 | Delta Time Extension and Next-day Cutoff | 35 | Extends the live end by 15 or 30 minutes on a late accepted bid, and stops at the next-day cutoff. |
|  | Module total | 175 |  |

## 11. Live Auction Monitoring and Closure

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F11-001 | Live Auction Monitoring Console | 52 | Authority view of live status, items, activity, remaining time, and extensions. |
| F11-002 | Authorised Force Close | 24 | Authority closes a live auction early, with a mandatory reason. |
| F11-003 | Scheduled Closure and Bid Freeze | 31 | Closes the auction at the effective end and freezes accepted bids for ranking. |
|  | Module total | 107 |  |

## 12. Results, Finalisation and Approval

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F12-001 | Item and Lot Bid Ranking | 60 | Ranks closed bids H1/H2/H3 or L1/L2/L3 per item or lot, and leaves ties unbroken. |
| F12-002 | Successful Bidder Finalisation | 59 | Selects the successful bidder per item or lot, including an explicit choice when the top rank is tied. |
| F12-003 | Finalisation Approval | 45 | Approves the successful-bidder selection or sends it back before award. |
|  | Module total | 164 |  |

## 13. Award and Letter of Intent

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F13-001 | Award Review and Approval | 47 | Records the award once finalisation is approved. No contract or payment. |
| F13-002 | Letter of Intent Generation | 54 | Generates the Letter of Intent from the awarded result for the successful bidder only. |
| F13-003 | Auction Completion and Successful-bidder Advice | 28 | Advises the successful bidder and marks the auction complete after the letter is issued. |
|  | Module total | 129 |  |

## 14. Notifications

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F14-001 | Lifecycle Notification Events and In-portal Alerts | 45 | In-portal alerts for the auction lifecycle events, targeted to the right person. |
| F14-002 | Email Delivery of Auction Notifications | 45 | Emails the lifecycle alerts and records whether delivery succeeded. |
|  | Module total | 90 |  |

## 15. Auction Status and History

| Feature | Name | Hours | What it covers |
| --- | --- | --- | --- |
| F15-001 | Auction Lifecycle Status | 36 | Shows the current auction stage, including the evaluation branch and force close. |
| F15-002 | Auction History for Authorised Users | 45 | Staff trace the auction from draft to completion. Bidders see only their own allowed events. |
|  | Module total | 81 |  |

# Effort profile

The largest features by hours are:

F02-005 Catalogue Item Maintenance — Category and Catalogue Management — 88 hours

F10-001 Live Bid Submission — Live Auction Bidding and Extension — 84 hours

F09-001 Participation Evaluation and Eligibility Decision — Pre-Live Participation Evaluation — 74 hours

F05-001 Auction Review and Decision — Auction Review, Approval and Publication — 63 hours

F06-001 Corrigendum Draft and Approval — Corrigendum Management — 61 hours

F04-003 Catalogue Item Selection and Lot Organisation — Auction Creation — 61 hours

F12-001 Item and Lot Bid Ranking — Results, Finalisation and Approval — 60 hours

F12-002 Successful Bidder Finalisation — Results, Finalisation and Approval — 59 hours

F08-001 Pre-auction Query and Clarification — Pre-Auction Query and Clarification — 59 hours

F03-004 Bidder Profile, Organisation and Documents — Bidder Registration and Profile — 57 hours

Hours by kind of module:

Shared platform: 165 hours (7.6%)

Business: 1916 hours (88.3%)

Notifications and delivery: 90 hours (4.1%)

# Indicative delivery sequence

Delivery is a single release. Work proceeds from staff access and the catalogue, to bidder onboarding, auction drafting and publication, participation and queries, pre-live evaluation, live bidding and closure, ranking and award, then alerts and the auction history. Forward and reverse auctions, item-wise and lot-wise bidding, corrigendum, the 15 and 30 minute extension, and force close are all in that release.

# Not included in these hours

Hosting, servers, certificates, and network provision

Payment gateway collection, refund, or forfeiture of earnest money

Contract, purchase order, delivery, invoicing, or settlement after the Letter of Intent

SMS and mobile applications

Migration of a previous auction system

Tax calculation, foreign-currency conversion, digital signature, and finance-system posting

Classroom training and post-go-live support retainers

# Planning assumptions

1. Staff access is by named user and role, with department as the organisational attribute. Bidder access is a separate portal account.

2. Earnest money is recorded as an amount, an instrument or reference, and a proof document. It is not collected through a payment service.

3. The price format records whether bids are inclusive or exclusive of GST. The system does not calculate tax.

4. A reserve price can be stored and shown when the auction says to show it. A bid is not rejected only because of the reserve.

5. The minimum bid movement is captured when the auction is created, because live bidding must enforce it.

6. Automatic extension is 15 or 30 minutes, and it stops at the auction’s next-day cutoff.

7. When two bidders share the top rank, a person chooses the successful bidder and records why. The system does not choose by itself.

8. Every corrigendum is approved before bidders see it. The accepted-bidder list is approved before a live auction that uses evaluation.

9. Alerts are shown in the portal and sent by email. SMS is not included.

10. Letter wording is supplied by the organisation. The letter is filled from the auction, the notice number, the bidder, the item or lot, and the result.

11. No previous-system data is loaded. Volumes for concurrent bidders were not stated in the source and remain a capacity input.

12. Documents and approvals sit inside the auction processes. They are not separate products.

# Disclaimer

These figures are indicative. They are intended for planning and for commercial discussion against the Statement of Work. A change to scope, volumes, approval rules, or the treatment of earnest money will change the hours. They are not a fixed quotation until both parties confirm the baseline and the assumptions above.