Module & Feature-wise Effort Estimate

BDA Post-Auction Award, Payment and Completion Management Module

Prepared for Bangalore Development Authority (BDA) · Client Copy · Effort in person-hours

Date: 2026-10-14

# 1. Introduction

This document sets out the module and feature-wise effort for the BDA Auction Module (Post-Auction). The Module takes each awarded site from the KPPP auction result to the completion of the auction process: result intake and verification, bidder intimation, instalment collection and reconciliation, Deputy Secretary processing, draft sale deed, registration recording and completion, with a bilingual Bidder Tracking Portal, dashboards and reports.

Hours cover the design and build of the application software, its integrations, security and audit controls, operational tooling and migration utilities, with associated testing and technical documentation.

Hours do not cover project management, the requirement study and prototype phase, training and help material, the VAPT service, on-site staffing, warranty and operation and maintenance, or hosting and third-party service charges.

# 2. Summary Totals

| Bucket | Person-hours |
| --- | --- |
| Recommended for go-live | 4766 |
| Conditional (subject to departmental permission) | 49 |
| Total (all items) | 4815 |
| Modules | 16 |
| Features | 75 |

# 3. Module-wise Summary

| Module | Type | Features | Hours | % of go-live |
| --- | --- | --- | --- | --- |
| 01. User, Role & Access Management | Shared | 4 | 515 | 10.8% |
| 02. Auction Rules & Configuration | Business | 6 | 499 | 10.5% |
| 03. KPPP Result Intake & Site Package | Business | 5 | 502 | 10.5% |
| 04. Result Verification & Approval | Business | 5 | 400 | 8.4% |
| 05. Successful Bidder Notification & Account | Business | 4 | 233 | 4.9% |
| 06. Payment & Instalment Management | Business | 9 | 766 | 16.1% |
| 07. Case Forwarding & Deputy Secretary Processing | Business | 5 | 293 | 6.1% |
| 08. Draft Sale Deed | Business | 4 | 182 | 3.8% |
| 09. Registration Recording & Completion | Business | 4 | 175 | 2.6% |
| 10. Bidder Tracking Portal | Business | 5 | 169 | 3.5% |
| 11. Dashboards, MIS & Reports | Business | 5 | 235 | 4.9% |
| 12. Notification Service | Shared | 4 | 199 | 4.2% |
| 13. Integration Hub | Technical | 4 | 223 | 4.7% |
| 14. Audit, Security & Compliance | Technical | 4 | 192 | 4.0% |
| 15. Platform Operations & Support | Technical | 4 | 121 | 2.5% |
| 16. Legacy Case Migration | Technical | 3 | 111 | 2.3% |
| Total |  | 75 | 4815 | 100% |

# 4. Feature-wise Detail

## 01. User, Role & Access Management

Staff login and sessions, user and role management, configurable permissions with DS-wise isolation, officer DSC registration.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F01-001 | Staff Authentication & Session Security | 136 | Recommended for go-live |
| F01-002 | Staff User Management & Role Assignment | 142 | Recommended for go-live |
| F01-003 | Permission Matrix & DS-wise Data Isolation | 147 | Recommended for go-live |
| F01-004 | Officer DSC Registration & Signing Authority | 90 | Recommended for go-live |
|  | Module total | 515 |  |

## 02. Auction Rules & Configuration

Instalment and payment rules, DS area allocation, approval hierarchy and thresholds, stage timelines, document templates, reference masters.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F02-001 | Instalment & Payment Rule Configuration | 105 | Recommended for go-live |
| F02-002 | Deputy Secretary Area Allocation Rules | 88 | Recommended for go-live |
| F02-003 | Approval Hierarchy & Bid Threshold Configuration | 90 | Recommended for go-live |
| F02-004 | Stage Timeline & Escalation Configuration | 62 | Recommended for go-live |
| F02-005 | Document Template Management | 89 | Recommended for go-live |
| F02-006 | Reference Masters | 65 | Recommended for go-live |
|  | Module total | 499 |  |

## 03. KPPP Result Intake & Site Package

KPPP API receipt, controlled report upload, matching and exceptions, CDRMS site package, locking and versioned re-import.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F03-001 | KPPP Result Receipt through API | 135 | Recommended for go-live |
| F03-002 | Controlled KPPP Result Report Upload | 96 | Recommended for go-live |
| F03-003 | Result-to-Site Matching & Exception Resolution | 84 | Recommended for go-live |
| F03-004 | CDRMS Site Package Retrieval & Case File Creation | 111 | Recommended for go-live |
| F03-005 | Result Locking & Versioned Re-import | 76 | Recommended for go-live |
|  | Module total | 502 |  |

## 04. Result Verification & Approval

Result review workbench, single-bidder and abnormal bid flags, multi-level DSC approval, draft proceedings, rejected / unsold intimation.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F04-001 | Site-wise Result Review Workbench | 109 | Recommended for go-live |
| F04-002 | Single-Bidder & Abnormal Bid Flagging | 60 | Recommended for go-live |
| F04-003 | Multi-Level Result Approval Workflow | 129 | Recommended for go-live |
| F04-004 | Draft Proceedings Generation | 55 | Recommended for go-live |
| F04-005 | Rejected & Unsold Site Intimation | 47 | Recommended for go-live |
|  | Module total | 400 |  |

## 05. Successful Bidder Notification & Account

Bidder account creation, OTP login and profile, bilingual DSC-signed intimation letter, dispatch with delivery status.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F05-001 | Bidder Account Creation | 68 | Recommended for go-live |
| F05-002 | Bidder OTP Login & Profile | 57 | Recommended for go-live |
| F05-003 | Bilingual Signed Intimation Letter | 61 | Recommended for go-live |
| F05-004 | Result Intimation Dispatch & Delivery Status | 47 | Recommended for go-live |
|  | Module total | 233 |  |

## 06. Payment & Instalment Management

Instalment demands, online and offline payments, daily reconciliation, ledger, reminders, extensions, defaults and disputes.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F06-001 | Instalment Schedule & Demand Generation | 70 | Recommended for go-live |
| F06-002 | Online Instalment Payment & Receipt | 145 | Recommended for go-live |
| F06-003 | Offline Payment Recording & Verification | 76 | Recommended for go-live |
| F06-004 | Daily Bank Reconciliation | 112 | Recommended for go-live |
| F06-005 | Payment Status & Ledger Tracking | 74 | Recommended for go-live |
| F06-006 | Payment Reminders & Overdue Monitoring | 51 | Recommended for go-live |
| F06-007 | Payment Extension Requests | 78 | Recommended for go-live |
| F06-008 | Default, Cancellation & Forfeiture Proceedings | 102 | Recommended for go-live |
| F06-009 | Payment Dispute Handling | 58 | Recommended for go-live |
|  | Module total | 766 |  |

## 07. Case Forwarding & Deputy Secretary Processing

Automatic forwarding by area on 75% payment, re-assignment, case file workspace, processing and document requests, timelines and alerts.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F07-001 | Automatic Case Forwarding by Area | 38 | Recommended for go-live |
| F07-002 | Case Re-assignment | 43 | Recommended for go-live |
| F07-003 | Deputy Secretary Case File Workspace | 95 | Recommended for go-live |
| F07-004 | Case Processing, Document Requests & Bidder Uploads | 76 | Recommended for go-live |
| F07-005 | Processing Timelines & Pending Case Alerts | 41 | Recommended for go-live |
|  | Module total | 293 |  |

## 08. Draft Sale Deed

Template-based draft sale deed, review and approval with versions and DSC, bidder access, final instalment trigger.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F08-001 | Draft Sale Deed Generation | 64 | Recommended for go-live |
| F08-002 | Sale Deed Review, Approval & Version History | 63 | Recommended for go-live |
| F08-003 | Bidder Access to Draft Sale Deed | 32 | Recommended for go-live |
| F08-004 | Final Instalment Demand Trigger | 23 | Recommended for go-live |
|  | Module total | 182 |  |

## 09. Registration Recording & Completion

Registration reference and deed copy, Kaveri exchange where permitted, completion record, status update to allotment section and CDRMS.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F09-001 | Registration Details Recording | 33 | Recommended for go-live |
| F09-002 | Kaveri Registration Data Exchange (Conditional) | 49 | Conditional — subject to departmental permission |
| F09-003 | Auction Process Completion | 40 | Recommended for go-live |
| F09-004 | Completion Status Sharing with Allotment Section & CDRMS | 53 | Recommended for go-live |
|  | Module total | 175 |  |

## 10. Bidder Tracking Portal

My awarded sites, site details and eleven-stage tracker, payments and receipts, documents, notifications and profile, bilingual GIGW portal.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F10-001 | My Awarded Sites | 27 | Recommended for go-live |
| F10-002 | Awarded Site Details & Stage Tracker | 39 | Recommended for go-live |
| F10-003 | Bidder Payment History & Receipts | 29 | Recommended for go-live |
| F10-004 | Bidder Documents, Notifications & Profile | 32 | Recommended for go-live |
| F10-005 | Bilingual, Responsive & GIGW-Compliant Portal | 42 | Recommended for go-live |
|  | Module total | 169 |  |

## 11. Dashboards, MIS & Reports

Commissioner, DS and Finance dashboards, standard MIS reports, configurable report builder.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F11-001 | Commissioner & Management Dashboard | 54 | Recommended for go-live |
| F11-002 | Deputy Secretary Dashboard | 31 | Recommended for go-live |
| F11-003 | Finance Dashboard | 31 | Recommended for go-live |
| F11-004 | Standard MIS Reports | 53 | Recommended for go-live |
| F11-005 | Configurable Report Builder | 66 | Recommended for go-live |
|  | Module total | 235 |  |

## 12. Notification Service

Bilingual DLT templates, stage event engine, e-mail / SMS / WhatsApp connectors, delivery log.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F12-001 | Bilingual Notification Template Management | 42 | Recommended for go-live |
| F12-002 | Stage Event Notification Engine | 48 | Recommended for go-live |
| F12-003 | Email, SMS & WhatsApp Gateway Connectors | 76 | Recommended for go-live |
| F12-004 | Notification Delivery Log | 33 | Recommended for go-live |
|  | Module total | 199 |  |

## 13. Integration Hub

Connector framework and credentials, integration monitoring and error queue, DSC / e-Sign service, Web GIS map.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F13-001 | Integration Framework & Credential Management | 57 | Recommended for go-live |
| F13-002 | Integration Monitoring & Error Queue | 46 | Recommended for go-live |
| F13-003 | DSC & e-Sign Signing Service | 82 | Recommended for go-live |
| F13-004 | BDA Web GIS Map Integration | 38 | Recommended for go-live |
|  | Module total | 223 |  |

## 14. Audit, Security & Compliance

Hash-chained audit trail, audit viewer and Section 63 support, security controls, DPDP compliance.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F14-001 | Tamper-Evident Audit Trail | 41 | Recommended for go-live |
| F14-002 | Audit Viewer & Evidence Certificate Support | 54 | Recommended for go-live |
| F14-003 | Application Security Controls | 51 | Recommended for go-live |
| F14-004 | Personal Data Protection Compliance | 46 | Recommended for go-live |
|  | Module total | 192 |  |

## 15. Platform Operations & Support

Environments and releases, backup and DR, monitoring and SLA reporting, support helpdesk.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F15-001 | Environments, CI/CD & Release Management | 27 | Recommended for go-live |
| F15-002 | Backup, Recovery & Disaster Recovery | 23 | Recommended for go-live |
| F15-003 | Monitoring, Availability & SLA Reporting | 34 | Recommended for go-live |
| F15-004 | Support Helpdesk & Ticket Tracking | 37 | Recommended for go-live |
|  | Module total | 121 |  |

## 16. Legacy Case Migration

Migration templates and staging, validation and reconciliation, activation of migrated cases at the correct stage.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F16-001 | Migration Templates & Staging Load | 39 | Recommended for go-live |
| F16-002 | Migration Validation & Reconciliation | 42 | Recommended for go-live |
| F16-003 | Migrated Case Activation | 30 | Recommended for go-live |
|  | Module total | 111 |  |

# 5. Conditional Items and Commercial Line Items

| Item | Basis |
| --- | --- |
| F09-002 Kaveri Registration Data Exchange | 49 person-hours, taken up only if the Department of Stamps and Registration permits data exchange |
| Operation and maintenance for three years from go-live | Quoted separately as part (b) of the financial proposal |
| On-site team during implementation and support | As per the minimum team in the RFP |
| Change of scope | At the man-month rate quoted in the financial proposal |

# 6. Effort Profile

| Work area | Hours | % of total |
| --- | --- | --- |
| User interface (screens and portal pages) | 1360 | 28.2% |
| Application services and business rules | 2140 | 44.4% |
| Data model and storage | 223 | 4.6% |
| Integrations | 212 | 4.4% |
| Testing | 724 | 15.0% |
| Documentation | 156 | 3.2% |

Largest features by effort:

| Feature ID | Feature Name | Hours |
| --- | --- | --- |
| F01-003 | Permission Matrix & DS-wise Data Isolation | 147 |
| F06-002 | Online Instalment Payment & Receipt | 145 |
| F01-002 | Staff User Management & Role Assignment | 142 |
| F01-001 | Staff Authentication & Session Security | 136 |
| F03-001 | KPPP Result Receipt through API | 135 |
| F04-003 | Multi-Level Result Approval Workflow | 129 |
| F06-004 | Daily Bank Reconciliation | 112 |
| F03-004 | CDRMS Site Package Retrieval & Case File Creation | 111 |
| F04-001 | Site-wise Result Review Workbench | 109 |
| F02-001 | Instalment & Payment Rule Configuration | 105 |

| Module type | Hours | % of total |
| --- | --- | --- |
| Business | 3454 | 71.7% |
| Shared | 714 | 14.8% |
| Technical | 647 | 13.4% |

# 7. Indicative Delivery Phasing

| Phase | Timeline | Scope |
| --- | --- | --- |
| Requirements and design | T + 21 to T + 30 days | System Requirement Specification, KPPP and CDRMS integration study, payment and area rules, UI/UX prototype |
| Foundation | T + 30 to T + 45 days | Access and roles, rules and templates, notifications, integration services, audit and security, environments |
| Result to intimation | T + 40 to T + 60 days | KPPP intake and site package, verification and approval, bidder account and intimation |
| Payments to completion | T + 50 to T + 75 days | Instalments and reconciliation, DS processing, draft sale deed, registration and completion |
| Portal, MIS and migration | T + 60 to T + 90 days | Bidder Tracking Portal, dashboards and reports, legacy case migration |
| Acceptance and go-live | T + 75 to T + 100 days | UAT, VAPT clearance, training and go-live; final acceptance at T + 160 days |

# 8. Items Not Included in Feature Hours

Project management, System Requirement Specification and UI/UX prototype

Training for BDA officials (minimum two rounds), bidder help guide and video tutorials

VAPT by a CERT-In empanelled auditor before go-live and annually

On-site deployment of professionals during implementation and support

Warranty (one year) and operation and maintenance (three years)

Hosting infrastructure, payment gateway, SMS, WhatsApp and e-mail charges, DSC tokens and certificates

Live bidding, pre-auction activities, EMD handling and bidder registration (performed on KPPP)

Registration of the sale deed (Department of Stamps and Registration)

# 9. Key Planning Assumptions

KPPP provides auction results through an API; where it does not, standard KPPP result reports are uploaded through the controlled upload facility, which is included.

CDRMS provides read access to the site package and accepts completion status updates.

BDA provides the e-payment gateway, bank settlement data, e-mail, SMS (with DLT registration) and WhatsApp accounts, and the e-Sign / DSC arrangement.

Approving officers hold valid DSC tokens.

BDA provides approved templates for letters, proceedings, notices and the draft sale deed, and the payment and area allocation rules.

Legacy pending cases are provided by BDA in the agreed migration templates.

Hosting is provided at the Karnataka State Data Centre or on BDA-specified infrastructure.

Access is role-based with Deputy Secretary-wise data isolation; bidders use a separate OTP login.

# 10. Disclaimer

Estimates are indicative for planning and commercial discussion. Final effort may vary with the KPPP and CDRMS integration positions confirmed in the requirement study, the payment gateway and bank formats, the e-Sign approach, the volume and quality of legacy data, and any scope changes agreed with BDA.