Module & Feature-wise Effort Estimate

Online Computer Literacy Test (CLT) and Digital Certification System

Prepared for Karnataka State Electronics Development Corporation Limited (KEONICS) · Client Copy · Effort in person-hours

Date: 2026-10-14

# 1. Introduction

This document sets out the module and feature-wise effort for the Online Computer Literacy Test (CLT) and Digital Certification System for KEONICS on behalf of the Center for E-Governance. The system covers the full CLT cycle: public portal and mobile application, candidate registration with HRMS validation and Aadhaar eKYC, online test booking with fees and hall tickets, the question bank and authoring tool, paper generation and mock tests, test centre operations, the online examination with English and Kannada typing tests, screen and webcam video proctoring, evaluation, digitally signed certificates, central monitoring, MIS and legacy data porting.

Hours cover the design and build of the application software, its integrations, security and audit controls, performance engineering for 2,000 concurrent candidates, operational tooling and porting utilities, with associated testing and technical documentation.

Hours do not cover project management, the FRS and design phase, question content creation, helpdesk staffing, the Safe-to-Host audit, training and how-to videos, warranty and comprehensive AMC, or hosting and third-party service charges.

# 2. Summary Totals

| Bucket | Person-hours |
| --- | --- |
| Recommended for go-live | 5136 |
| Conditional (taken up only if required by KEONICS) | 50 |
| Total (all items) | 5186 |
| Modules | 18 |
| Features | 90 |

# 3. Module-wise Summary

| Module | Type | Features | Hours | % of go-live |
| --- | --- | --- | --- | --- |
| 01. Access Control & Staff User Management | Shared | 3 | 316 | 6.2% |
| 02. Examination Configuration & Masters | Business | 6 | 360 | 7.0% |
| 03. CLT Web Portal & Mobile Application | Business | 4 | 230 | 4.5% |
| 04. Candidate Registration & eKYC | Business | 6 | 423 | 8.2% |
| 05. Online Test Booking, Fees & Hall Ticket | Business | 6 | 361 | 7.0% |
| 06. Question Bank & Content Authoring Tool | Business | 8 | 470 | 8.2% |
| 07. Question Paper Generation & Mock Test | Business | 4 | 176 | 3.4% |
| 08. Test Centre Operations & Candidate Validation | Business | 6 | 320 | 6.2% |
| 09. Online Examination Engine | Business | 7 | 474 | 9.2% |
| 10. Screen Proctoring & Malpractice Management | Business | 6 | 391 | 7.6% |
| 11. Evaluation, Results & Digital Certification | Business | 6 | 253 | 4.9% |
| 12. Central Monitoring Centre & Examination Monitoring Unit | Business | 4 | 219 | 4.3% |
| 13. MIS, Dashboards & Reports | Business | 4 | 181 | 3.5% |
| 14. Notifications & Helpdesk | Shared | 4 | 192 | 3.7% |
| 15. Integration Hub | Technical | 6 | 393 | 7.7% |
| 16. Security, Audit & Compliance | Technical | 4 | 185 | 3.6% |
| 17. Platform, Performance & Operations | Technical | 4 | 159 | 3.1% |
| 18. Legacy CLT Data Porting | Technical | 2 | 83 | 1.6% |
| Total |  | 90 | 5186 | 100% |

# 4. Feature-wise Detail

## 01. Access Control & Staff User Management

Staff login with OTP, user and role management with centre and district mapping, configurable permission matrix and data scope.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F01-001 | Staff Authentication & Session Security | 107 | Recommended for go-live |
| F01-002 | Staff User, Role & Centre Mapping | 106 | Recommended for go-live |
| F01-003 | Permission Matrix & Data Scope | 103 | Recommended for go-live |
|  | Module total | 316 |  |

## 02. Examination Configuration & Masters

Syllabus, marks and weightage with session snapshot, test centres and seats, session calendar and batch rules, fee rules, document templates, reference masters.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F02-001 | Syllabus, Marks & Weightage Configuration | 88 | Recommended for go-live |
| F02-002 | Test Centre, Seat & Terminal Master | 70 | Recommended for go-live |
| F02-003 | Session Calendar & Batch Rules | 62 | Recommended for go-live |
| F02-004 | Fee Rule Configuration | 45 | Recommended for go-live |
| F02-005 | Document & Certificate Template Management | 60 | Recommended for go-live |
| F02-006 | Reference Masters | 35 | Recommended for go-live |
|  | Module total | 360 |  |

## 03. CLT Web Portal & Mobile Application

Public portal at clt.karnataka.gov.in with test information, centres and study material, content management, responsive bilingual design and a candidate mobile application.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F03-001 | Public Information Portal | 56 | Recommended for go-live |
| F03-002 | Portal Content & Study Material Management | 42 | Recommended for go-live |
| F03-003 | Bilingual, Responsive & Device-Agnostic Design | 34 | Recommended for go-live |
| F03-004 | Candidate Mobile Application | 98 | Recommended for go-live |
|  | Module total | 230 |  |

## 04. Candidate Registration & eKYC

Candidate OTP account, KGID registration with HRMS validation, eKYC registration for prospective candidates and employees without KGID, centre-assisted registration, scrutiny, scribe requests.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F04-001 | Candidate OTP Login & Account | 90 | Recommended for go-live |
| F04-002 | Government Employee Registration with KGID & HRMS Validation | 90 | Recommended for go-live |
| F04-003 | Prospective Candidate & Non-KGID Registration with eKYC | 92 | Recommended for go-live |
| F04-004 | Centre-Assisted Registration & Photo Capture | 52 | Recommended for go-live |
| F04-005 | Registration Scrutiny & Metadata Validation | 66 | Recommended for go-live |
| F04-006 | Differently-Abled Candidate Support Requests | 33 | Recommended for go-live |
|  | Module total | 423 |  |

## 05. Online Test Booking, Fees & Hall Ticket

Online Test Booking System with colour-coded slots, attempt-based fees and payment, receipts and reconciliation, barcode hall ticket, one-time self-service rescheduling, minimum batch and forced rescheduling.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F05-001 | Online Test Booking & Slot Availability | 88 | Recommended for go-live |
| F05-002 | Attempt-Based Fee Calculation & Online Payment | 68 | Recommended for go-live |
| F05-003 | Payment Receipt, Reconciliation & Exceptions | 64 | Recommended for go-live |
| F05-004 | Hall Ticket with Barcode & Receipt | 43 | Recommended for go-live |
| F05-005 | Candidate Self-Service Rescheduling | 34 | Recommended for go-live |
| F05-006 | Minimum Batch Check & Forced Rescheduling | 64 | Recommended for go-live |
|  | Module total | 361 |  |

## 06. Question Bank & Content Authoring Tool

Question paper guidelines and blueprint, bilingual rich-content authoring, maker-checker and Technical Committee approval, component segregation, calibration, bulk import, mock and main banks, typing passages.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F06-001 | Question Paper Guidelines & Blueprint | 58 | Recommended for go-live |
| F06-002 | Bilingual Rich-Content Question Authoring | 119 | Recommended for go-live |
| F06-003 | Maker-Checker & Technical Committee Approval | 76 | Recommended for go-live |
| F06-004 | Question Component Segregation & Bank Privacy | 48 | Recommended for go-live |
| F06-005 | Field Test & Difficulty Calibration | 50 | Conditional — taken up only if required by KEONICS |
| F06-006 | Excel / CSV Question Import | 44 | Recommended for go-live |
| F06-007 | Mock & Main Question Bank Management | 46 | Recommended for go-live |
| F06-008 | Typing Test Passage Management | 29 | Recommended for go-live |
|  | Module total | 470 |  |

## 07. Question Paper Generation & Mock Test

Weightage and difficulty based random paper set per session, question and option jumbling per candidate, sealed paper release, mock test engine.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F07-001 | Weightage & Difficulty-Based Paper Generation | 66 | Recommended for go-live |
| F07-002 | Question & Option Jumbling per Candidate | 31 | Recommended for go-live |
| F07-003 | Sealed Paper Storage & Session Release | 40 | Recommended for go-live |
| F07-004 | Mock Test Engine | 39 | Recommended for go-live |
|  | Module total | 176 |  |

## 08. Test Centre Operations & Candidate Validation

Proctor management and attendance, centre sanity check and session start, candidate identity validation and photo, biometric / Aadhaar authentication, seat allocation, attendance sheets and scans.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F08-001 | Proctor Management, Authentication & Attendance | 57 | Recommended for go-live |
| F08-002 | Centre Readiness Check & Session Start | 58 | Recommended for go-live |
| F08-003 | Candidate Identity Validation & Photo Capture | 64 | Recommended for go-live |
| F08-004 | Biometric & Aadhaar Authentication at Centre | 56 | Recommended for go-live |
| F08-005 | Seat Allocation & Hall Ticket Login Control | 41 | Recommended for go-live |
| F08-006 | Attendance Sheets, Scans & Centre Incident Records | 44 | Recommended for go-live |
|  | Module total | 320 |  |

## 09. Online Examination Engine

Secure login and language choice, rich MCQ interface, server-synchronised timer with compensation, English and Kannada typing test, autosave and integrity, submission with immediate score, device-agnostic secure client.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F09-001 | Secure Test Login & Language Selection | 52 | Recommended for go-live |
| F09-002 | Rich MCQ Delivery & Navigation | 90 | Recommended for go-live |
| F09-003 | Server-Synchronised Timer & Disruption Compensation | 60 | Recommended for go-live |
| F09-004 | English & Kannada Typing Test | 66 | Recommended for go-live |
| F09-005 | Response Autosave & Answer Integrity | 64 | Recommended for go-live |
| F09-006 | Submission, Early Exit & Immediate Score | 35 | Recommended for go-live |
| F09-007 | Secure Exam Client & Device Compatibility | 107 | Recommended for go-live |
|  | Module total | 474 |  |

## 10. Screen Proctoring & Malpractice Management

Continuous screen video recording, webcam video recording with automated monitoring, browser activity and tab-switch detection, real-time alerts, malpractice cases and reports, recording storage and playback.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F10-001 | Continuous Screen Recording | 62 | Recommended for go-live |
| F10-002 | Webcam Recording & Automated Monitoring | 88 | Recommended for go-live |
| F10-003 | Browser Activity & Tab-Switch Detection | 35 | Recommended for go-live |
| F10-004 | Real-Time Suspicious Activity Alerts | 68 | Recommended for go-live |
| F10-005 | Malpractice Case Management & Reports | 72 | Recommended for go-live |
| F10-006 | Recording Storage, Playback & Retention | 66 | Recommended for go-live |
|  | Module total | 391 |  |

## 11. Evaluation, Results & Digital Certification

Automatic MCQ and typing evaluation with optional negative marking, answer key challenge, result finalisation with signed submission, digitally signed certificate, certificate issue workflow, public verification.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F11-001 | Automatic MCQ & Typing Evaluation | 50 | Recommended for go-live |
| F11-002 | Answer Key Challenge | 52 | Recommended for go-live |
| F11-003 | Result Finalisation & Signed Submission | 50 | Recommended for go-live |
| F11-004 | Digitally Signed Certificate Generation | 42 | Recommended for go-live |
| F11-005 | Certificate Issue Workflow & Download | 39 | Recommended for go-live |
| F11-006 | Public Certificate Verification | 20 | Recommended for go-live |
|  | Module total | 253 |  |

## 12. Central Monitoring Centre & Examination Monitoring Unit

Real-time monitoring of all centres and sessions, exam-day control actions and venue change handling, central monitoring reports, post-test wrap-up and archival.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F12-001 | Real-Time Centre & Session Monitoring | 70 | Recommended for go-live |
| F12-002 | Exam-Day Control & Venue Change Handling | 72 | Recommended for go-live |
| F12-003 | Central Monitoring Reports | 37 | Recommended for go-live |
| F12-004 | Post-Test Wrap-Up & Archival | 40 | Recommended for go-live |
|  | Module total | 219 |  |

## 13. MIS, Dashboards & Reports

Management dashboard, registration, test and result MIS, question bank quarterly and enhancement reports, data retrieval and query tool.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F13-001 | Management Dashboard | 44 | Recommended for go-live |
| F13-002 | Registration, Test & Result MIS Reports | 66 | Recommended for go-live |
| F13-003 | Question Bank Quarterly Reports | 25 | Recommended for go-live |
| F13-004 | Data Retrieval & Query Tool | 46 | Recommended for go-live |
|  | Module total | 181 |  |

## 14. Notifications & Helpdesk

Bilingual notification templates and event engine, e-mail and SMS gateways, helpdesk ticketing with call logging, delivery log.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F14-001 | Notification Templates & Event Engine | 48 | Recommended for go-live |
| F14-002 | E-mail & SMS Gateway Integration | 57 | Recommended for go-live |
| F14-003 | Helpdesk Ticketing & Call Logging | 60 | Recommended for go-live |
| F14-004 | Notification Delivery Log | 27 | Recommended for go-live |
|  | Module total | 192 |  |

## 15. Integration Hub

Integration framework and monitoring, HRMS fetch and result push, Aadhaar authentication and eKYC, payment gateway, HSM, DSC / e-Sign.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F15-001 | Integration Framework & Monitoring | 57 | Recommended for go-live |
| F15-002 | HRMS Integration | 82 | Recommended for go-live |
| F15-003 | Aadhaar Authentication & eKYC Integration | 76 | Recommended for go-live |
| F15-004 | Payment Gateway Integration | 56 | Recommended for go-live |
| F15-005 | HSM Key Management Integration | 68 | Recommended for go-live |
| F15-006 | DSC & e-Sign Integration | 54 | Recommended for go-live |
|  | Module total | 393 |  |

## 16. Security, Audit & Compliance

AES-256 and asymmetric encryption with HSM keys, tamper-evident audit trail per Annexure 9, application security and Safe-to-Host support, DPDP compliance.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F16-001 | Data Encryption & Key Management | 37 | Recommended for go-live |
| F16-002 | Tamper-Evident Audit Trail | 59 | Recommended for go-live |
| F16-003 | Application Security & Safe-to-Host Support | 39 | Recommended for go-live |
| F16-004 | DPDP Compliance & Aadhaar Data Vault | 50 | Recommended for go-live |
|  | Module total | 185 |  |

## 17. Platform, Performance & Operations

SDC deployment and hardening, scalability for 2,000 concurrent candidates and load testing, backup and retention, availability monitoring and SLA reporting.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F17-001 | SDC Deployment, Hardening & Release Management | 38 | Recommended for go-live |
| F17-002 | Scalability & Load Testing for 2,000 Concurrent Candidates | 50 | Recommended for go-live |
| F17-003 | Backup, Restore & Data Retention | 25 | Recommended for go-live |
| F17-004 | Availability Monitoring & SLA Reporting | 46 | Recommended for go-live |
|  | Module total | 159 |  |

## 18. Legacy CLT Data Porting

Templates and porting of previous CLT data, validation and reconciliation with sign-off.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F18-001 | Legacy Data Templates & Porting | 53 | Recommended for go-live |
| F18-002 | Ported Data Validation & Reconciliation | 30 | Recommended for go-live |
|  | Module total | 83 |  |

# 5. Conditional Items and Commercial Line Items

| Item | Basis |
| --- | --- |
| F06-005 Field Test & Difficulty Calibration | 50 person-hours, taken up only if KEONICS requires field testing and calibration |
| Question content creation by Subject Matter Experts | At least 2,000 bilingual questions at launch and 5% growth per year; quoted separately |
| Helpdesk with dedicated numbers | Need-based offsite helpdesk; quoted separately |
| Safe-to-Host audit and SSL certificates | Annual audit by a CERT-In empanelled auditor; at actuals |
| Comprehensive AMC for three years after warranty | Quoted separately, payable quarterly |
| Change of scope | At the rate quoted in the financial proposal |

# 6. Effort Profile

| Work area | Hours | % of total |
| --- | --- | --- |
| User interface (screens and portal pages) | 1572 | 30.3% |
| Application services and business rules | 2150 | 41.5% |
| Data model and storage | 255 | 4.9% |
| Integrations | 296 | 5.7% |
| Testing | 724 | 14.0% |
| Documentation | 189 | 3.6% |

Largest features by effort:

| Feature ID | Feature Name | Hours |
| --- | --- | --- |
| F06-002 | Bilingual Rich-Content Question Authoring | 119 |
| F01-001 | Staff Authentication & Session Security | 107 |
| F09-007 | Secure Exam Client & Device Compatibility | 107 |
| F01-002 | Staff User, Role & Centre Mapping | 106 |
| F01-003 | Permission Matrix & Data Scope | 103 |
| F03-004 | Candidate Mobile Application | 98 |
| F04-003 | Prospective Candidate & Non-KGID Registration with eKYC | 92 |
| F04-001 | Candidate OTP Login & Account | 90 |
| F04-002 | Government Employee Registration with KGID & HRMS Validation | 90 |
| F09-002 | Rich MCQ Delivery & Navigation | 90 |

| Module type | Hours | % of total |
| --- | --- | --- |
| Business | 3858 | 74.4% |
| Shared | 508 | 9.8% |
| Technical | 820 | 15.8% |

# 7. Indicative Delivery Phasing

| Phase | Timeline | Scope |
| --- | --- | --- |
| Functional Requirement Specification | T + 1 month | Requirements for all modules, integration positions, test pattern and rules |
| Design and foundation | T + 0.5 to T + 1.5 months | UI/UX, MIS design, technology stack, server requirements, data migration document; access, configuration, notifications, integrations, security and environments |
| Candidate journey and question bank | T + 1 to T + 2 months | Portal and mobile application, registration and eKYC, booking, fees and hall ticket, authoring tool, question bank and paper generation |
| Examination and certification | T + 1 to T + 2 months | Test centre operations, secure exam client and examination engine, video proctoring, evaluation, certificates, central monitoring |
| MIS and data porting | T + 1.5 to T + 2 months | Dashboards, reports, query tool, legacy CLT data porting |
| User acceptance testing | T + 2 to T + 2.5 months | UAT at SDC, load testing at 2,000 concurrent candidates |
| Safe-to-Host and go-live | T + 2.5 to T + 3 months | Safe-to-Host certification, go-live with ten trouble-free sessions, source code handover |

# 8. Items Not Included in Feature Hours

Project management and the FRS and design documentation phase

Question content creation by Subject Matter Experts and Technical Committee costs

Helpdesk staffing and dedicated helpdesk numbers

Safe-to-Host audit by a CERT-In empanelled auditor and SSL certificates

Training, user manuals and how-to videos

Warranty (12 months) and comprehensive AMC (three years)

Exit management and knowledge transfer

SDC hosting, storage and bandwidth; payment gateway, SMS, e-mail, Aadhaar and e-Sign charges

Test centre premises, terminals, webcams and network

# 9. Key Planning Assumptions

HRMS provides employee look-up by KGID and accepts the update of results and certificates.

Aadhaar authentication and eKYC are available through the state AUA / KUA arrangement.

The Center for E-Governance HSM and signing certificates are available for key management and digital signatures.

KEONICS provides the payment gateway, SMS (with DLT registration) and e-mail accounts.

SDC provides compute, storage for screen and webcam recordings and bandwidth as per the agreed capacity plan.

Test centres provide terminals with webcams and network, and permit installation of the secure exam client.

The English and Kannada typing tests form Part 2 of the examination; the Kannada keyboard layout is confirmed in the FRS.

Legacy CLT data is provided by KEONICS in the agreed templates.

Access is role-based with district and centre data scope; candidates use a separate OTP login.

# 10. Disclaimer

Estimates are indicative for planning and commercial discussion. Final effort may vary with the HRMS, Aadhaar, HSM and signing positions confirmed in the FRS, the proctoring and recording parameters, centre terminal configurations, the volume and quality of legacy data, and any scope changes agreed with KEONICS.