Module & Feature-wise Effort Estimate

Guest House Booking and Access Management Platform

Client Copy · Effort in person-hours

Date: 2026-09-22 · Project code: GHB

# 1. Introduction

This document presents an indicative module and feature-wise effort estimate for the Guest House Booking and Access Management Platform.

Hours cover application software design and build for the Phase 1 web platform, including employee booking, payments, access credentials, administration, and required integrations.

Hours do not cover payment gateway or SMS commercial charges, access-control hardware supply/installation, hosting consumption, AMC, classroom training delivery, native mobile apps, or legacy data migration.

# 2. Summary Totals

| Bucket | Person-hours |
| --- | --- |
| Recommended go-live | 1601 |
| Optional / conditional (hardware path) | 158 |
| All-in | 1759 |
| Modules | 8 |
| Features | 30 |

# 3. Module-wise Summary

| Module | Type | Features | Hours | % of go-live |
| --- | --- | --- | --- | --- |
| 01. User Registration & Authentication | Shared | 4 | 226 | 14.1% |
| 02. Site, Building & Room Configuration | Business | 4 | 240 | 15.0% |
| 03. Booking & Room Allocation | Business | 5 | 256 | 16.0% |
| 04. Online Payment Processing | Business | 3 | 152 | 9.5% |
| 05. Access Credentials & Guest Check-in | Business | 5 | 254 | 15.9% |
| 06. Administration, Monitoring & Reports | Business | 4 | 217 | 13.6% |
| 07. Notification Service | Technical | 2 | 111 | 6.9% |
| 08. Integration Hub | Technical | 3 | 303 | 18.9% |

# 4. Feature-wise Detail

## 01. User Registration & Authentication

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F01-001 | Mobile OTP Registration | 40 | Recommended for Phase 1 go-live |
| F01-002 | Government Identity Submission | 77 | Recommended for Phase 1 go-live |
| F01-003 | Secure Login and Session Management | 46 | Recommended for Phase 1 go-live |
| F01-004 | Role and Permission Assignment | 63 | Recommended for Phase 1 go-live |
|  | Module subtotal | 226 |  |

## 02. Site, Building & Room Configuration

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F02-001 | Site and Location Master | 54 | Recommended for Phase 1 go-live |
| F02-002 | Building and Floor Setup | 60 | Recommended for Phase 1 go-live |
| F02-003 | Room Catalogue and Pricing | 75 | Recommended for Phase 1 go-live |
| F02-004 | Heterogeneous Property Structures | 51 | Recommended for Phase 1 go-live |
|  | Module subtotal | 240 |  |

## 03. Booking & Room Allocation

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F03-001 | Inventory Browse and Availability Search | 62 | Recommended for Phase 1 go-live |
| F03-002 | Booking Request with Conflict Prevention | 75 | Recommended for Phase 1 go-live |
| F03-003 | Booking Summary and Pricing Preview | 34 | Recommended for Phase 1 go-live |
| F03-004 | Automatic Room Allocation | 45 | Recommended for Phase 1 go-live |
| F03-005 | Booking Confirmation Record | 40 | Recommended for Phase 1 go-live |
|  | Module subtotal | 256 |  |

## 04. Online Payment Processing

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F04-001 | Payment Checkout Initiation | 41 | Recommended for Phase 1 go-live |
| F04-002 | Payment Success Handling | 55 | Recommended for Phase 1 go-live |
| F04-003 | Payment Failure Retry and Status | 56 | Recommended for Phase 1 go-live |
|  | Module subtotal | 152 |  |

## 05. Access Credentials & Guest Check-in

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F05-001 | Access Credential Generation | 44 | Recommended for Phase 1 go-live |
| F05-002 | Credential Delivery | 38 | Recommended for Phase 1 go-live |
| F05-003 | Self Check-in and Occupancy Tracking | 79 | Recommended for Phase 1 go-live |
| F05-004 | Optional Hardware Access Handoff | 62 | Optional where access hardware is available |
| F05-005 | Manual Key Override Recording | 31 | Recommended for Phase 1 go-live |
|  | Module subtotal | 254 |  |

## 06. Administration, Monitoring & Reports

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F06-001 | Operations Dashboard | 54 | Recommended for Phase 1 go-live |
| F06-002 | Administrative Master and User Controls | 31 | Recommended for Phase 1 go-live |
| F06-003 | Exceptional Booking Override | 67 | Recommended for Phase 1 go-live |
| F06-004 | Activity Revenue and Utilization Reports | 65 | Recommended for Phase 1 go-live |
|  | Module subtotal | 217 |  |

## 07. Notification Service

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F07-001 | Notification Template Catalogue | 56 | Recommended for Phase 1 go-live |
| F07-002 | Notification Dispatch and Status | 55 | Recommended for Phase 1 go-live |
|  | Module subtotal | 111 |  |

## 08. Integration Hub

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F08-001 | Payment Gateway Adapter | 130 | Recommended for Phase 1 go-live |
| F08-002 | Communication Service Adapter | 77 | Recommended for Phase 1 go-live |
| F08-003 | Access-Control Hardware Adapter | 96 | Optional where access hardware is available |
|  | Module subtotal | 303 |  |

# 5. Optional Commercial Line Items

| Item | Hours | Notes |
| --- | --- | --- |
| Access-control hardware enablement | 158 | Credential sync to door hardware plus adapter; quote when sites are equipped |

# 6. Effort Profile

| Rank | Feature | Module | Hours |
| --- | --- | --- | --- |
| 1 | F08-001 Payment Gateway Adapter | Integration Hub | 130 |
| 2 | F08-003 Access-Control Hardware Adapter | Integration Hub | 96 |
| 3 | F05-003 Self Check-in and Occupancy Tracking | Access Credentials & Guest Check-in | 79 |
| 4 | F08-002 Communication Service Adapter | Integration Hub | 77 |
| 5 | F01-002 Government Identity Submission | User Registration & Authentication | 77 |
| 6 | F03-002 Booking Request with Conflict Prevention | Booking & Room Allocation | 75 |
| 7 | F02-003 Room Catalogue and Pricing | Site, Building & Room Configuration | 75 |
| 8 | F06-003 Exceptional Booking Override | Administration, Monitoring & Reports | 67 |

| Module type | Hours |
| --- | --- |
| Business | 1119 |
| Shared | 226 |
| Technical | 414 |

# 7. Indicative Delivery Phasing

Foundation: user registration and access, property configuration, notification service, and payment/communication integrations.

Booking core: availability search, booking with conflict prevention, payment, allocation, and confirmation.

Arrival and operations: access credentials, check-in and occupancy, dashboards, overrides, and reports.

Optional: automated door-access hardware path for equipped sites only.

# 8. Items Not Included in Feature Hours

Payment gateway merchant account fees and SMS/email commercial costs

Supply and installation of locks or access-control hardware

Cloud/hosting consumption, AMC, and on-site training delivery beyond basic documentation

Native mobile applications

Integration to a centralized government employee directory

Legacy data migration

# 9. Key Planning Assumptions

End users are authorized government employees.

Payment gateway and communication services are provisioned by the client.

Access-control hardware availability varies by location; core booking does not depend on hardware.

Access model is User to Role to Permissions.

Phase 1 identity validation is document submission with configurable administrative verification status.

Network connectivity is available at guest-house locations for online operations.

# 10. Disclaimer

Estimates are indicative for planning and commercial discussion. Final effort may vary based on clarified identity-verification depth, payment-gateway specifics, hardware vendors, and change requests agreed during delivery.