Module & Feature-wise Effort Estimate

Garrison Online Moulding Catalogue Platform

Prepared for Garrison Industries · Effort in person-hours

Date: 2026-10-05 · Project code: GMC

# 1. Introduction

This document presents a module and feature-wise effort estimate for the Garrison Online Moulding Catalogue Platform. The platform comprises a public, responsive online moulding catalogue integrated with the Garrison website, a secure administration portal, and a structured catalogue data framework that lets Garrison add categories, attributes and products without software changes.

Hours cover the design and build of application software: configuration and data framework, administration and publishing workflow, public catalogue pages, search and filters, enquiry handling, SEO and website integration, import tooling for the initial catalogue, security, environments and deployment, with associated testing and documentation.

Hours do not cover project management, the UX/UI design phase, initial catalogue population labour (priced per product), hosting and third-party service charges, independent penetration testing, or annual support and maintenance.

# 2. Summary Totals

| Bucket | Person-hours |
| --- | --- |
| Recommended go-live | 4057 |
| Optional | 68 |
| Total (all items) | 4125 |
| Modules | 13 |
| Features | 53 |

# 3. Module-wise Summary

| Module | Type | Features | Hours | % of total |
| --- | --- | --- | --- | --- |
| 01. Administrator Access & Role Management | Shared | 4 | 397 | 9.6% |
| 02. Catalogue Taxonomy & Master Data | Business | 3 | 215 | 5.2% |
| 03. Dynamic Attribute & Dimension Framework | Business | 4 | 350 | 8.5% |
| 04. Product Profile Management | Business | 7 | 550 | 13.3% |
| 05. Combinations & Product Relationships | Business | 3 | 228 | 5.5% |
| 06. Content Governance & Publishing Workflow | Business | 5 | 483 | 11.7% |
| 07. External Source, Provenance & Content Rights | Business | 3 | 215 | 5.2% |
| 08. Public Catalogue Experience | Business | 5 | 389 | 9.4% |
| 09. Search & Filtering | Business | 4 | 317 | 7.7% |
| 10. Product Enquiry | Business | 3 | 150 | 3.6% |
| 11. SEO, Analytics & Website Integration | Shared | 4 | 254 | 6.2% |
| 12. Catalogue Data Import & Bulk Operations | Technical | 4 | 342 | 8.3% |
| 13. Platform Security, Performance & Operations | Technical | 4 | 235 | 5.7% |
| Total |  | 53 | 4125 | 100% |

# 4. Feature-wise Detail

## 01. Administrator Access & Role Management

Admin sign-in and session security, user management, configurable role permissions, audit log.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F01-001 | Administrator Authentication & Session Security | 104 | Recommended for go-live |
| F01-002 | Administrator User Management | 103 | Recommended for go-live |
| F01-003 | Role & Permission Configuration | 98 | Recommended for go-live |
| F01-004 | Administrative Audit Log | 92 | Recommended for go-live |
|  | Module total | 397 |  |

## 02. Catalogue Taxonomy & Master Data

Categories and sub-categories, styles, collections, materials/species, finishes.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F02-001 | Category & Sub-category Management | 98 | Recommended for go-live |
| F02-002 | Style & Collection Management | 58 | Recommended for go-live |
| F02-003 | Material, Species & Finish Masters | 59 | Recommended for go-live |
|  | Module total | 215 |  |

## 03. Dynamic Attribute & Dimension Framework

Attribute library, category attribute templates, template change impact, dimension normalisation.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F03-001 | Attribute Library & Units of Measure | 96 | Recommended for go-live |
| F03-002 | Category Attribute Templates | 115 | Recommended for go-live |
| F03-003 | Template Change Impact Management | 72 | Recommended for go-live |
| F03-004 | Dimension Normalisation & Display Formatting | 67 | Recommended for go-live |
|  | Module total | 350 |  |

## 04. Product Profile Management

Product register, core profile, dynamic dimensions, materials/finishes/lengths, media, documents, lifecycle, preview.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F04-001 | Product Register & Core Profile | 141 | Recommended for go-live |
| F04-002 | Category-driven Dimension & Attribute Entry | 84 | Recommended for go-live |
| F04-003 | Materials, Finishes, Lengths & Applications | 57 | Recommended for go-live |
| F04-004 | Product Media & Drawing Management | 98 | Recommended for go-live |
| F04-005 | Technical Document Management | 53 | Recommended for go-live |
| F04-006 | Product Duplicate, Archive & Restore | 67 | Recommended for go-live |
| F04-007 | Product Preview | 50 | Recommended for go-live |
|  | Module total | 550 |  |

## 05. Combinations & Product Relationships

Typed product relationships; combinations as separate entity with component assembly.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F05-001 | Typed Product Relationships | 74 | Recommended for go-live |
| F05-002 | Combination Record Management | 90 | Recommended for go-live |
| F05-003 | Combination Component Assembly | 64 | Recommended for go-live |
|  | Module total | 228 |  |

## 06. Content Governance & Publishing Workflow

Completeness and duplicate rules, submit/review/approve, publish/unpublish, workflow emails.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F06-001 | Data Completeness & Duplicate Validation | 107 | Recommended for go-live |
| F06-002 | Submit for Review & Review Queue | 93 | Recommended for go-live |
| F06-003 | Review Decision & Approval History | 100 | Recommended for go-live |
| F06-004 | Publish, Unpublish & Bulk Publishing | 102 | Recommended for go-live |
| F06-005 | Workflow Email Notifications | 81 | Recommended for go-live |
|  | Module total | 483 |  |

## 07. External Source, Provenance & Content Rights

External source register, per-product provenance, rights-based publication gate and dashboard.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F07-001 | External Source Register | 45 | Recommended for go-live |
| F07-002 | Product Provenance Capture | 82 | Recommended for go-live |
| F07-003 | Content Rights Publication Gate & Rights Dashboard | 88 | Recommended for go-live |
|  | Module total | 215 |  |

## 08. Public Catalogue Experience

Catalogue home, listings, product detail, combination detail, responsive design system.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F08-001 | Catalogue Home Page | 56 | Recommended for go-live |
| F08-002 | Category, Style & Collection Listing Pages | 99 | Recommended for go-live |
| F08-003 | Product Detail Page | 110 | Recommended for go-live |
| F08-004 | Combination Detail Page | 55 | Recommended for go-live |
| F08-005 | Responsive Catalogue Design System & Accessibility | 69 | Recommended for go-live |
|  | Module total | 389 |  |

## 09. Search & Filtering

Search index sync, ranked keyword/code/dimension search, configurable facets, suggestions.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F09-001 | Search Index & Publication Synchronisation | 86 | Recommended for go-live |
| F09-002 | Global Keyword, Code & Dimension Search | 79 | Recommended for go-live |
| F09-003 | Configurable Faceted Filters | 96 | Recommended for go-live |
| F09-004 | Search Suggestions & Results Experience | 56 | Recommended for go-live |
|  | Module total | 317 |  |

## 10. Product Enquiry

Contextual enquiry form, routing and acknowledgement emails, basic enquiry register.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F10-001 | Product Enquiry Form | 51 | Recommended for go-live |
| F10-002 | Enquiry Routing & Acknowledgement | 46 | Recommended for go-live |
| F10-003 | Enquiry Register | 53 | Recommended for go-live |
|  | Module total | 150 |  |

## 11. SEO, Analytics & Website Integration

SEO URLs/metadata/redirects, sitemap and structured data, Garrison website integration, usage analytics.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F11-001 | SEO URLs, Metadata & Redirects | 80 | Recommended for go-live |
| F11-002 | Sitemap, Structured Data & Social Metadata | 43 | Recommended for go-live |
| F11-003 | Garrison Website Integration | 69 | Recommended for go-live |
| F11-004 | Catalogue Usage Analytics | 62 | Recommended for go-live |
|  | Module total | 254 |  |

## 12. Catalogue Data Import & Bulk Operations

Import templates and validation, bulk media matching, staging and commit, optional export/bulk update.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F12-001 | Import Templates & Bulk Product Import | 115 | Recommended for go-live |
| F12-002 | Bulk Media Upload & Auto-matching | 68 | Recommended for go-live |
| F12-003 | Import Staging Review & Commit | 91 | Recommended for go-live |
| F12-004 | Catalogue Export & Bulk Update | 68 | Optional (recommended) |
|  | Module total | 342 |  |

## 13. Platform Security, Performance & Operations

Media processing and CDN, security hardening, backup and monitoring, environments and deployment.

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F13-001 | Media Processing & Content Delivery | 72 | Recommended for go-live |
| F13-002 | Security Hardening & Upload Protection | 60 | Recommended for go-live |
| F13-003 | Backup, Monitoring & Error Logging | 52 | Recommended for go-live |
| F13-004 | Environments & Deployment Pipeline | 51 | Recommended for go-live |
|  | Module total | 235 |  |

# 5. Optional Items and Commercial Line Items

| Item | Basis |
| --- | --- |
| F12-004 Catalogue Export & Bulk Update | 68 person-hours (optional software feature) |
| Initial catalogue population — up to the agreed product count | One-time fixed price, based on the product count confirmed at discovery |
| Additional product population beyond the agreed quantity | Per product |
| Support and maintenance (AMC) | Annual |

# 6. Effort Profile

| Work area | Hours | % of total |
| --- | --- | --- |
| User interface (screens and pages) | 1382 | 33.5% |
| Application services and business logic | 1576 | 38.2% |
| Data model and storage | 193 | 4.7% |
| Integrations and environments | 156 | 3.8% |
| Testing | 710 | 17.2% |
| Documentation | 108 | 2.6% |

# 7. Indicative Delivery Phasing

Foundation: administrator access, taxonomy and masters, attribute and dimension framework, environments and release automation.

Catalogue core: product profiles, media and documents, combinations and relationships, completeness rules and the review and publishing workflow.

Population tooling: import templates, bulk media matching, staging and commit, running in parallel with catalogue data preparation.

Customer experience: catalogue home, listings, product and combination pages, search and filters, enquiry.

Go-live readiness: SEO, website integration, analytics, security hardening, backup and monitoring, testing and acceptance.

# 8. Items Not Included in Feature Hours

Project management, discovery workshops and the UX/UI design phase

Initial catalogue population labour (data extraction, normalisation, drawing preparation) — priced per product

Hosting, CDN, email, analytics and search service subscriptions

Obtaining third-party content rights or permissions

Independent penetration testing

E-commerce, pricing, inventory, customer accounts, CRM or ERP integration

Multilingual content

Annual support and maintenance after the warranty period

# 9. Key Planning Assumptions

The platform is a digital product catalogue; visitors do not log in.

Administrator access uses configurable roles: Super Administrator, Catalogue Administrator, Catalogue Reviewer and Content Administrator.

Garrison provides website and hosting access, brand assets, catalogue source files and service accounts (email, analytics, spam protection) on time.

The catalogue integrates with the Garrison website through a sub-path or sub-domain confirmed during discovery.

A dedicated search capability is available within the agreed hosting environment.

Garrison approves taxonomy, external product inclusion and the initial dataset, and confirms third-party content rights.

Content is in English; dimensions are primarily in inches with optional millimetre display.

The initial product count is agreed during discovery.

# 10. Disclaimer

Estimates are indicative for planning and commercial discussion. Final effort may vary with the confirmed website platform and hosting environment, the agreed initial product count, the quality of source catalogue material, and any scope changes agreed during discovery.