Garrison Website & Moulding Catalogue — Consolidated Estimate

Client: Garrison Industries

Date: 2026-10-07

Effort unit: person-hours

# 1. Introduction

This document brings together three options for Garrison Industries' website and moulding catalogue. Garrison has advised that products change rarely, so Options 1 and 2 set up the catalogue once and have no administration portal. Option 3 is the full platform with self-service administration.

Option 1 — Website design and product migration: new website design and build, with the Brenlo moulding products and their details migrated once.

Option 2 — Option 1 plus AI product images: as Option 1, with original AI-assisted product images and lifestyle imagery instead of copied photographs.

Option 3 — Premium online catalogue platform: the same new website design and company pages as Options 1 and 2, plus admin portal, configurable catalogue, publishing workflow, rights tracking, bulk import and advanced search.

# 2. Summary of Options

| Item | Option 1: Website and Products | Option 2: Website, Products and AI Pictures | Option 3: Premium Catalogue Platform |
| --- | --- | --- | --- |
| Number of features | 23 | 29 | 59 |
| Website and feature development (hours) | 690 | 864 | 3,476 |
| Product, page and picture setup (hours) | 88 | 228 | 18 |
| Total effort (hours) | 778 | 1,092 | 3,494 |
| AI picture service charges (paid at actual cost, in addition to the hours) | Not applicable | USD 162 to 532, capped at USD 600 | Not applicable |
| Estimated timeline | About 7 weeks, team of 3 | About 10 weeks, team of 3 | About 15 to 18 weeks, team of 5 to 6 |

# 3. Options Matrix

All three options include the same new website. The main difference is who looks after the product catalogue once the website is live.

Options 1 and 2: We set up the products once. Any later changes are made by our developer.

Option 3: Garrison gets its own easy-to-use control panel, so its staff can add, edit, review and publish products themselves. The product pages also carry much more detail.

| Feature | Option 1: Website and Products | Option 2: Website, Products and AI Pictures | Option 3: Premium Catalogue Platform |
| --- | --- | --- | --- |
| Website | 284 hours | 284 hours | 248 hours |
| New website design, including the home page and company pages | Yes | Yes | Yes |
| Content moved over from the current website | Yes | Yes | Yes |
| Contact form | Enquiries are emailed to Garrison | Enquiries are emailed to Garrison | Each enquiry goes to the right person, and all enquiries are kept in one list |
| What visitors see | 142 hours | 142 hours | 685 hours |
| Product page | Code, size, style, wood type and one picture | Same as Option 1 | Everything in Option 1, plus a description, a profile drawing visitors can zoom into, finish colours, available lengths, more pictures and downloadable product sheets |
| Product filters | Style, thickness, width and wood type | Same as Option 1 | More filters, such as finish, use, collection and height, which Garrison can change itself |
| Search | By code, type, style or size | Same as Option 1 | Same as Option 1, with suggestions as you type |
| Related products | Similar sizes are shown automatically | Same as Option 1 | Garrison picks the matching products, such as the casing that goes with a crown |
| Trim combinations (mouldings shown together as a set) | No | No | Yes, with each part linked to its own product page |
| Product collections chosen by Garrison | No | No | Yes. Garrison can create its own collections, such as Best Sellers, Colonial Look (a matching crown, casing and baseboard) or In Stock in Cayman, and each one gets its own page |
| Products and pictures | 233 hours | 547 hours | 219 hours |
| Setting up the products at the start | We transfer the products once, and Garrison approves the list in a spreadsheet | Same as Option 1 | Garrison uploads the products from a spreadsheet itself, at launch and at any time later |
| Product pictures | Brenlo's existing pictures (Brenlo's permission is required) | New pictures made with AI for all 350 products. Each product is first drawn to its exact shape, then given a realistic finish and checked by our team. Room and banner pictures for the website are also included | Several pictures per product, from Brenlo or from Garrison's own photography, uploaded by Garrison |
| Product sheets and installation guides (PDF downloads) | No | No | Yes |
| Adding a new product type, such as doors | Needs new development work | Needs new development work | Garrison sets it up itself, with no development needed |
| Managing the catalogue (behind the scenes) | Not included | Not included | 1,950 hours |
| Product changes after go-live | Made by our developer on request | Made by our developer on request | Made by Garrison's own staff at any time |
| Staff logins | No | No | Yes, with different access levels, such as edit only or edit and approve |
| Approval before a product goes live | Garrison reviews the spreadsheet once, before launch | Garrison reviews the spreadsheet once, before launch | A manager reviews and approves every change before it goes live |
| Showing or hiding a product | Done by our developer | Done by our developer | Done by Garrison in one click |
| Change history | No | No | Yes, a full record of who changed what and when |
| Permission to use Brenlo's content | Garrison confirms once | Garrison confirms once, and we keep a record of how each AI picture was made | Recorded for each product, and nothing without permission can go live |
| Going live and running the website | 119 hours | 119 hours | 392 hours |
| Google search setup | Set up at launch | Same as Option 1 | Set up at launch and updated automatically when products change |
| Visitor reports | Pages and products viewed, and enquiries received | Same as Option 1 | More detail, including searches that found no results |
| Hosting and upkeep | Simple, low-cost hosting | Same as Option 1 | Higher hosting cost, with automatic backups, monitoring and extra security |
| Cost of changes after go-live | Developer time for each change | Developer time for each change, plus AI charges for any new pictures | No developer cost for product changes |
| Total effort (hours) | 778 | 1,092 | 3,494 |

The hours shown on each section row are the effort for that section.

# 4. What the Extra Cost of Option 2 Pays For

Option 2 has the same product work as Option 1, plus about 314 hours to create a new, accurate picture for each of the 350 products instead of using Brenlo's photos. This is why 'Products and pictures' is 547 hours in Option 2 and 233 hours in Option 1.

| Part of the work | Option 1 | Option 2 |
| --- | --- | --- |
| Copying the product details from Brenlo, tidying them up, Garrison's spreadsheet check and loading them into the website | 141 | 141 |
| Product pictures: copying Brenlo's photos (Option 1), or keeping them only as private references (Option 2) | 22 | 11 |
| Checking each product's details (350 products × 0.2 hours) | 70 | 70 |
| Agreeing the picture style and a trial on 20 products | — | 38 |
| Tool for drawing each product's outline | — | 28 |
| Turning each outline into a 3D picture and adding a realistic finish with AI | — | 48 |
| Screen for checking and choosing the best picture for each product | — | 34 |
| Room and banner pictures for the website | — | 25 |
| 'Illustrative picture' labels and a record of how each picture was made | — | 12 |
| Drawing each product's outline at its real size (350 products × 0.24 hours) | — | 84 |
| Checking and choosing each AI picture (350 products × 0.16 hours) | — | 56 |
| Total | 233 | 547 |

### Why each picture needs work

An AI tool cannot draw a correct moulding just from its name. Asked for a '5¼-inch colonial crown', it draws a crown that looks right but has the wrong shape. Because visitors choose mouldings by their exact shape, every picture must be accurate. For each product we:

Draw the real outline of the moulding at its real size.

Turn the outline into a plain 3D picture, so the shape is exactly right.

Let the AI add a realistic wood or paint finish and lighting.

Check the picture against the outline before it goes on the website.

Steps 1 and 4 are repeated for all 350 products (140 hours). The remaining 185 hours set up the process once. AI service fees are separate (see the summary table).

### Ways to reduce the cost of Option 2

| Choice | Saving | What changes |
| --- | --- | --- |
| Garrison provides its own drawings of its profiles | Most of the 84 hours of outline drawing | Depends on Garrison having the drawings |
| Leave out the room and banner pictures | 25 hours | Use stock photos or Garrison's own photos instead |
| Let the AI create pictures without the outline and 3D steps | About 150 hours | Pictures will often show the wrong shape, which is risky for a product catalogue |
| Use AI only for room, banner and category pictures; product pages show a clean outline drawing | Roughly 250–300 hours (quoted on request) | Product pictures look technical rather than like photographs |

# 5. What the Extra Cost of Option 3 Pays For

Option 3 costs about 2,716 hours more than Option 1. The website part is about the same in both. The difference is in the products: Option 1 spends 494 hours setting them up once, while Option 3 spends 3,246 hours on Garrison's own control panel and richer product pages.

Most of this work is in the control panel, the screens Garrison staff use to manage products. Visitors never see it, which is why the difference is hard to spot just by looking at the website. The table shows what the extra hours pay for.

| What Garrison gets | What it means | Hours |
| --- | --- | --- |
| Staff logins and access levels | Each staff member has their own login. Garrison decides who can edit and who can approve, and can see who changed what | 317 |
| Setting up product types, styles and wood types | Garrison can add or rename product types (crown, casing, baseboard), styles, product groups, wood types and finishes itself | 171 |
| The right details for each product type | Each product type shows its own details (for example a crown shows its angle; a door shows its height and panel style). New product types can be added without a developer | 281 |
| Adding and editing products | Simple forms for descriptions, sizes, finishes, lengths, pictures, drawings and PDF sheets. Copy a similar product to save time, hide old products and bring them back, and preview a page before it goes live | 440 |
| Matching products and trim combinations | Show which products go together (for example the casing that matches a crown) and build combinations from several products | 182 |
| Checking and approving before going live | Warns if something important is missing; a manager approves before publishing; show or hide one or many products at once; email reminders | 387 |
| Tracking permission to use Brenlo's content | Records where each product's details and pictures came from and whether Garrison may use them. Anything without permission cannot go live | 172 |
| Richer product pages for visitors | Drawings visitors can zoom into, size tables, finish colours and combination pages | 311 |
| Better search and product choices | Search stays up to date automatically, gives suggestions while typing, and Garrison chooses how visitors narrow down products | 254 |
| Handling enquiries | Each enquiry goes to the right person and is kept in a list so nothing is missed | 120 |
| Google listing and visitor reports | The Google listing updates itself when products change; detailed reports on what visitors look at and search for | 203 |
| Adding many products at once | Upload many products from a spreadsheet and many pictures in one go, check them on screen, then publish | 219 |
| Security, backups and reliability | Fast-loading pictures, protection against hackers and harmful files, automatic backups, monitoring, and a separate test website for trying changes safely | 189 |
| Total |  | 3,246 |

# 6. Everyday Situations After Go-live

What happens when Garrison wants to make common changes:

| Situation | Options 1 and 2 | Option 3 |
| --- | --- | --- |
| Add five new mouldings | Send the details to our developer. About 2–4 hours of work, usually done within a few working days | Staff add them in a simple form (or upload a spreadsheet), a manager approves, and they are live the same day |
| Remove a product that is no longer sold | Our developer makes the change (about 1 hour) | Hide it with one click |
| Start selling interior doors, which need different details (height, width, panel style) | New development, about 40 hours | Garrison sets up 'Doors' in the control panel and adds the products. No developer needed |
| Update the sizes of 100 products from a supplier's spreadsheet | Our developer updates the products and Garrison checks the spreadsheet again (about 4–8 hours) | Staff upload the spreadsheet, check the changes on screen and confirm |
| Add a drawing or an installation guide (PDF) to a product | Not possible without new development | Upload it on the product |
| Find out who changed a product and when | Ask our developer | Look at the product's change history |
| Show that Garrison is allowed to use a picture, if asked | Only the spreadsheet Garrison signed | Each product shows where its content came from and the permission |
| Follow up on enquiries | Search the email inbox | A list of all enquiries, showing which ones have been answered |

In Option 2, each new product also needs a new AI picture.

# 7. Which Option Is Right for Garrison

Option 1 is right if the product range will stay small and rarely change, Garrison is happy to ask a developer for the occasional change, and it wants the lowest cost and the quickest launch. Brenlo's permission to use its pictures is needed.

Option 2 is right in the same situation if Garrison prefers its own new pictures instead of using Brenlo's.

Option 3 is right if Garrison plans to sell more types of products (for example doors, sheet goods or products from other suppliers), several staff will look after the catalogue, it wants drawings and PDF sheets on product pages, it wants changes approved before they go live, or it does not want to rely on a developer for product changes.

Option 3 is an investment in a catalogue that Garrison runs and grows itself. If the range will stay as it is, Option 1 or 2 is the better value. Garrison can also start with Option 1 or 2 and move to Option 3 later: the product information we prepare can be loaded into Option 3, so that work is not wasted.

# 8. Option 1 — Website design and product migration: Features

### Option 1 · 01. Discovery & Website Design

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F01-001 | Existing Website Discovery & Content Capture | Review of the current Garrison website from its public pages | 27 |
| F01-002 | Information Architecture & Wireframes | New sitemap and navigation model covering the company pages and the product catalogue | 29 |
| F01-003 | Visual Design System & Page Designs | Brand-aligned visual design for the new website | 63 |
|  | Module total |  | 119 |

### Option 1 · 02. Website Build

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F02-001 | Site Foundation, Layout & Navigation | Technical foundation of the new website | 46 |
| F02-002 | Home Page | New home page | 25 |
| F02-003 | Company & Service Content Pages | Templates for Garrison's company pages | 28 |
| F02-004 | Contact & Enquiry Form | Contact page with enquiry form (name, email, phone, company, subject, message, optional product reference) | 36 |
| F02-005 | Existing Content Migration | Move the content Garrison keeps from the current site into the new templates | 12 |
|  | Module total |  | 147 |

### Option 1 · 03. Product Catalogue Pages

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F03-001 | Mouldings Landing Page | Catalogue entry page | 17 |
| F03-002 | Category Listing Page with Filters | Product grid per category showing image, code and thickness × width, with filters for style, thickness | 47 |
| F03-003 | Product Detail Page | Product page with image and lightbox, code, category, style, thickness and width (fraction display) | 39 |
| F03-004 | Catalogue Search | Search box with suggestions and a results page, matching product code (exact and prefix), category | 25 |
| F03-005 | Product Enquiry | Request Information action on product pages that opens the enquiry form (F02-004) with the product code | 14 |
|  | Module total |  | 142 |

### Option 1 · 04. One-time Product Data Migration

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F04-001 | Source Catalogue Extraction Utility | Command-line utility that walks the source catalogue's moulding categories and styles | 52 |
| F04-002 | Product Image Acquisition & Optimisation | Download every product image referenced in the raw dataset, verify it, rename it to a Garrison convention | 22 |
| F04-003 | Data Normalisation & Validation | Transform raw records into the master dataset | 42 |
| F04-004 | Garrison Review Workbook & Sign-off | Export the master dataset to an Excel review workbook | 22 |
| F04-005 | Catalogue Data Build & Publishing | Turn the frozen dataset into the website's catalogue data files (per category, per product and search index) | 25 |
|  | Module total |  | 163 |

### Option 1 · 05. Hosting, SEO & Launch

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F05-001 | SEO Foundation & Redirects | SEO-friendly URLs (for example /mouldings/crown/507), template-driven titles and meta descriptions | 23 |
| F05-002 | Hosting, Domain, SSL & DNS Cutover | Provision staging and production hosting for the new static site and form handler | 33 |
| F05-003 | Analytics & Cookie Consent | Web analytics with key events | 14 |
| F05-004 | Quality Assurance, Accessibility & Performance | Functional test cycle across all pages and catalogue features, cross-browser and device testing | 27 |
| F05-005 | UAT, Launch & Handover | Migration reconciliation report | 22 |
|  | Module total |  | 119 |

### Option 1 · Product, page and image effort

| Item | Quantity | Hours per item | Hours |
| --- | --- | --- | --- |
| Per-product data verification | 350 | 0.2 | 70 |
| Existing page content migration | 15 | 1.2 | 18 |
| Total |  |  | 88 |

Option 1 total: 690 feature hours + 88 product, page and image hours = 778 hours.

# 9. Option 2 — Website design, product migration and AI product images: Features

### Option 2 · 01. Discovery & Website Design

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F01-001 | Existing Website Discovery & Content Capture | Review of the current Garrison website from its public pages | 27 |
| F01-002 | Information Architecture & Wireframes | New sitemap and navigation model covering the company pages and the product catalogue | 29 |
| F01-003 | Visual Design System & Page Designs | Brand-aligned visual design for the new website | 63 |
|  | Module total |  | 119 |

### Option 2 · 02. Website Build

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F02-001 | Site Foundation, Layout & Navigation | Technical foundation of the new website | 46 |
| F02-002 | Home Page | New home page | 25 |
| F02-003 | Company & Service Content Pages | Templates for Garrison's company pages | 28 |
| F02-004 | Contact & Enquiry Form | Contact page with enquiry form (name, email, phone, company, subject, message, optional product reference) | 36 |
| F02-005 | Existing Content Migration | Move the content Garrison keeps from the current site into the new templates | 12 |
|  | Module total |  | 147 |

### Option 2 · 03. Product Catalogue Pages

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F03-001 | Mouldings Landing Page | Catalogue entry page | 17 |
| F03-002 | Category Listing Page with Filters | Product grid per category showing image, code and thickness × width, with filters for style, thickness | 47 |
| F03-003 | Product Detail Page | Product page with image and lightbox, code, category, style, thickness and width (fraction display) | 39 |
| F03-004 | Catalogue Search | Search box with suggestions and a results page, matching product code (exact and prefix), category | 25 |
| F03-005 | Product Enquiry | Request Information action on product pages that opens the enquiry form (F02-004) with the product code | 14 |
|  | Module total |  | 142 |

### Option 2 · 04. One-time Product Data Migration

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F04-001 | Source Catalogue Extraction Utility | Command-line utility that walks the source catalogue's moulding categories and styles | 52 |
| F04-002 | Reference Image Capture (Internal Use Only) | Download the source product images solely as internal references for profile silhouette preparation (F06-002) | 11 |
| F04-003 | Data Normalisation & Validation | Transform raw records into the master dataset | 42 |
| F04-004 | Garrison Review Workbook & Sign-off | Export the master dataset to an Excel review workbook | 22 |
| F04-005 | Catalogue Data Build & Publishing | Turn the frozen dataset into the website's catalogue data files (per category, per product and search index) | 25 |
|  | Module total |  | 152 |

### Option 2 · 05. Hosting, SEO & Launch

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F05-001 | SEO Foundation & Redirects | SEO-friendly URLs (for example /mouldings/crown/507), template-driven titles and meta descriptions | 23 |
| F05-002 | Hosting, Domain, SSL & DNS Cutover | Provision staging and production hosting for the new static site and form handler | 33 |
| F05-003 | Analytics & Cookie Consent | Web analytics with key events | 14 |
| F05-004 | Quality Assurance, Accessibility & Performance | Functional test cycle across all pages and catalogue features, cross-browser and device testing | 27 |
| F05-005 | UAT, Launch & Handover | Migration reconciliation report | 22 |
|  | Module total |  | 119 |

### Option 2 · 06. AI Product Imagery

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F06-001 | AI Imagery Style Guide, Model Setup & Pilot | Define the product image style (angle, lighting, background, wood or primed finish, shadow) | 38 |
| F06-002 | Profile Silhouette Preparation | Create a clean vector cross-section silhouette for each product, scaled to its published thickness × width | 28 |
| F06-003 | Base Render & AI Image Generation | Batch process that extrudes each silhouette into a 3D moulding segment and renders a neutral base image at the agreed angle | 48 |
| F06-004 | Image Review, Selection & Touch-up | Internal review gallery showing each product's candidates beside its silhouette and reference, with approve | 34 |
| F06-005 | Lifestyle & Category Hero Images | AI-generated scene images for the home page hero, category banners and supporting page imagery | 25 |
| F06-006 | AI Image Disclosure & Provenance Record | Show an 'illustrative image' note on product pages, embed provenance metadata | 12 |
|  | Module total |  | 185 |

### Option 2 · Product, page and image effort

| Item | Quantity | Hours per item | Hours |
| --- | --- | --- | --- |
| Per-product data verification | 350 | 0.2 | 70 |
| Existing page content migration | 15 | 1.2 | 18 |
| Profile silhouette preparation (operator time) | 350 | 0.24 | 84 |
| AI image review and selection | 350 | 0.16 | 56 |
| Total |  |  | 228 |

Option 2 total: 864 feature hours + 228 product, page and image hours = 1,092 hours.

AI service fees are paid at provider rates, separately from effort: about 1,850 image generations, USD 162 to 532, capped at USD 600, including 25% contingency.

# 10. Option 3 — Premium online catalogue platform with website design: Features

### Option 3 · 01. Administrator Access & Role Management

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F01-001 | Administrator Authentication & Session Security | Secure sign-in to the catalogue administration portal for Garrison staff with a strong password policy | 83 |
| F01-002 | Administrator User Management | Super Administrator maintains the list of portal users | 82 |
| F01-003 | Role & Permission Configuration | Configure roles and their permissions as a matrix of portal areas | 78 |
| F01-004 | Administrative Audit Log | Append-only log of every administrative create, update, delete, workflow, publication | 74 |
|  | Module total |  | 317 |

### Option 3 · 02. Catalogue Taxonomy & Master Data

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F02-001 | Category & Sub-category Management | Maintain the moulding category hierarchy | 78 |
| F02-002 | Style & Collection Management | Maintain styles (for example Classic, Traditional, Modern, Transitional, Colonial) and collections | 46 |
| F02-003 | Material, Species & Finish Masters | Maintain material/species values (for example Oak, Maple, Poplar, Pine, Cherry, MDF, Engineered) | 47 |
|  | Module total |  | 171 |

### Option 3 · 03. Dynamic Attribute & Dimension Framework

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F03-001 | Attribute Library & Units of Measure | Central library of attribute definitions used by category templates | 77 |
| F03-002 | Category Attribute Templates | Per-category template defining which attributes apply, in what order and group | 92 |
| F03-003 | Template Change Impact Management | When a template version is about to be published, analyse which existing products are affected | 58 |
| F03-004 | Dimension Normalisation & Display Formatting | Accept dimension input as fractional inches (3/4, 1-1/4, 1 1/4"), decimal inches (0.75 in) or millimetres | 54 |
|  | Module total |  | 281 |

### Option 3 · 04. Product Profile Management

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F04-001 | Product Register & Core Profile | Product register and core profile maintenance | 113 |
| F04-002 | Category-driven Dimension & Attribute Entry | Dynamic dimensions and attributes panel in the product workspace | 67 |
| F04-003 | Materials, Finishes, Lengths & Applications | Capture materials/species, finish options, available lengths | 46 |
| F04-004 | Product Media & Drawing Management | Typed media management per product | 78 |
| F04-005 | Technical Document Management | Upload and maintain technical PDFs | 42 |
| F04-006 | Product Duplicate, Archive & Restore | Duplicate an existing product as a template for a similar profile (choosing which sections to copy) | 54 |
| F04-007 | Product Preview | Render a draft or working-draft product using the actual public product page template, with a draft banner | 40 |
|  | Module total |  | 440 |

### Option 3 · 05. Combinations & Product Relationships

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F05-001 | Typed Product Relationships | Define typed relationships between profiles | 59 |
| F05-002 | Combination Record Management | Manage combinations (multi-profile assemblies shown in the Garrison catalogue) as a separate catalogue entity | 72 |
| F05-003 | Combination Component Assembly | Link component profiles to a combination with role/position | 51 |
|  | Module total |  | 182 |

### Option 3 · 06. Content Governance & Publishing Workflow

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F06-001 | Data Completeness & Duplicate Validation | Evaluate each product and combination against baseline mandatory rules | 86 |
| F06-002 | Submit for Review & Review Queue | Submit products and combinations (individually or in bulk) for review with a note to the reviewer | 74 |
| F06-003 | Review Decision & Approval History | Review workspace where the Catalogue Reviewer sees the item's data | 80 |
| F06-004 | Publish, Unpublish & Bulk Publishing | Publish approved products and combinations (individually or in bulk) | 82 |
| F06-005 | Workflow Email Notifications | Email notifications for workflow events | 65 |
|  | Module total |  | 387 |

### Option 3 · 07. External Source, Provenance & Content Rights

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F07-001 | External Source Register | Master of external reference sources (for example Brenlo and other approved industry catalogues) | 36 |
| F07-002 | Product Provenance Capture | Per-product provenance panel for externally referenced products | 66 |
| F07-003 | Content Rights Publication Gate & Rights Dashboard | Rules engine that blocks publication of third-party media or text when rights are 'To be confirmed' or usage | 70 |
|  | Module total |  | 172 |

### Option 3 · 08. Public Catalogue Experience

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F08-001 | Catalogue Home Page | Public catalogue landing page | 45 |
| F08-002 | Category, Style & Collection Listing Pages | Public listing pages for categories, sub-categories, styles and collections | 79 |
| F08-003 | Product Detail Page | Public product page combining technical and inspirational content | 88 |
| F08-004 | Combination Detail Page | Public combination page showing the assembly image and drawing, overall dimensions, description | 44 |
| F08-005 | Responsive Catalogue Design System & Accessibility | Brand-aligned responsive design system for the public catalogue | 55 |
|  | Module total |  | 311 |

### Option 3 · 09. Search & Filtering

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F09-001 | Search Index & Publication Synchronisation | Maintain a dedicated search index of Published products and combinations | 69 |
| F09-002 | Global Keyword, Code & Dimension Search | Global search across code, name, category, style, material, finish, dimension and keywords, | 63 |
| F09-003 | Configurable Faceted Filters | Faceted filtering driven by template configuration | 77 |
| F09-004 | Search Suggestions & Results Experience | Type-ahead suggestions grouped by product codes, products | 45 |
|  | Module total |  | 254 |

### Option 3 · 10. Product Enquiry

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F10-001 | Product Enquiry Form | Request Information form opened from product and combination pages | 41 |
| F10-002 | Enquiry Routing & Acknowledgement | Route each enquiry by email to Garrison recipients according to rules | 37 |
| F10-003 | Enquiry Register | Basic administrative register of enquiries with filters (date, category, product, role, status) | 42 |
|  | Module total |  | 120 |

### Option 3 · 11. SEO, Analytics & Website Integration

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F11-001 | SEO URLs, Metadata & Redirects | SEO-friendly URL scheme (for example /mouldings/crown/CM-001, /mouldings/combinations/CB-010) | 64 |
| F11-002 | Sitemap, Structured Data & Social Metadata | Automatically generated XML sitemap | 34 |
| F11-003 | Garrison Website Integration | Integrate the catalogue into the existing Garrison website | 55 |
| F11-004 | Catalogue Usage Analytics | Analytics event layer for catalogue interactions | 50 |
|  | Module total |  | 203 |

### Option 3 · 12. Catalogue Data Import & Bulk Operations

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F12-001 | Import Templates & Bulk Product Import | Generate category-specific import templates | 92 |
| F12-002 | Bulk Media Upload & Auto-matching | Upload images and drawings in bulk (ZIP or multi-file) | 54 |
| F12-003 | Import Staging Review & Commit | Review staged import rows in a spreadsheet-like grid with inline correction and re-validation | 73 |
|  | Module total |  | 219 |

### Option 3 · 13. Platform Security, Performance & Operations

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F13-001 | Media Processing & Content Delivery | Process uploaded images and drawings into optimised derivatives | 58 |
| F13-002 | Security Hardening & Upload Protection | Platform-wide security controls | 48 |
| F13-003 | Backup, Monitoring & Error Logging | Automated database and media backups with retention and a tested restore procedure, uptime and health checks | 42 |
| F13-004 | Environments & Deployment Automation | Development, staging and production environments; automated build | 41 |
|  | Module total |  | 189 |

### Option 3 · 14. Website Discovery & Design

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F14-001 | Existing Website Discovery & Content Capture | Review of the current Garrison website from its public pages | 27 |
| F14-002 | Information Architecture & Wireframes | New sitemap and navigation model covering the company pages and the product catalogue | 29 |
| F14-003 | Visual Design System & Page Designs | Brand-aligned visual design for the new website | 63 |
|  | Module total |  | 119 |

### Option 3 · 15. Website Build & Content Migration

| Feature ID | Feature | Description | Hours |
| --- | --- | --- | --- |
| F15-001 | Site Foundation, Layout & Navigation | Technical foundation of the new website | 46 |
| F15-002 | Home Page | New home page | 25 |
| F15-003 | Company & Service Content Pages | Templates for Garrison's company pages | 28 |
| F15-004 | Existing Content Migration | Move the content Garrison keeps from the current site into the new templates | 12 |
|  | Module total |  | 111 |

### Option 3 · Product, page and image effort

| Item | Quantity | Hours per item | Hours |
| --- | --- | --- | --- |
| Existing page content migration | 15 | 1.2 | 18 |
| Total |  |  | 18 |

Option 3 total: 3,476 feature hours + 18 product, page and image hours = 3,494 hours.

# 11. Key Assumptions

Planning quantities: 350 moulding products and about 15 existing website pages; extra items at the same per-item rates.

Options 1 and 2 rebuild the website from its public content; only domain/registrar access is needed, and company email records are preserved.

Garrison approves designs, content and the product list within two review rounds each.

In Options 1 and 2, later product changes are made by a developer.

Option 3 includes the same website design, home page, company pages and content migration as Options 1 and 2; its product enquiry module replaces the separate contact form. Administration portal screens follow the agreed design system.

Project management, hosting fees, third-party fees, copywriting and photography are not included in any option.

# 12. Content Rights

All options use Brenlo's product data; Garrison should hold Brenlo's written permission before publication. Option 2 avoids publishing Brenlo photographs, but the profiles shown remain Brenlo designs, and AI-assisted images carry their own considerations (accuracy, ownership, provider terms). Garrison's legal counsel should review the chosen option before go-live. This document is not legal advice.

# 13. Disclaimer

Estimates are indicative and subject to confirmation of product and page counts, approval turnaround, access to the source catalogue and, for Option 2, AI service pricing at the time of generation.