Effort Estimate

Garrison Website Design & Product Catalogue Migration (Option 1)

Prepared for Garrison Industries · Effort in person-hours

Date: 2026-10-07 · Project code: GWM

# 1. Introduction

This document estimates the effort to redesign the Garrison website (www.garrisonindustries.ky) and publish the moulding products from the Brenlo online catalogue on it.

Garrison has advised that products change rarely, so catalogue set-up (categories, styles, products and reference data) is done once and no administration portal is included. Garrison approves the product list through a review workbook; later changes are made by a developer. Because the current website's source code and admin logins are not available, the website is rebuilt from its public content in a new design; only domain access is needed.

# 2. Summary Totals

| Bucket | Person-hours |
| --- | --- |
| Software and design (included features) | 862 |
| Per-product data verification (350 × 0.25 h) | 88 |
| Existing page content migration (15 × 1.5 h) | 23 |
| Recommended total | 973 |
| Optional features | 70 |

# 3. Module-wise Summary

| Module | Features | Hours |
| --- | --- | --- |
| 01. Discovery & Website Design | 3 | 149 |
| 02. Website Build | 5 | 183 |
| 03. Product Catalogue Pages | 6 | 206 |
| 04. One-time Product Data Migration | 6 | 245 |
| 05. Hosting, SEO & Launch | 5 | 149 |
| Software total | 25 | 932 |

# 4. Feature-wise Detail

## 01. Discovery & Website Design

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F01-001 | Existing Website Discovery & Content Capture | 34 | Included |
| F01-002 | Information Architecture & Wireframes | 36 | Included |
| F01-003 | Visual Design System & Page Designs | 79 | Included |
|  | Module total | 149 |  |

## 02. Website Build

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F02-001 | Site Foundation, Layout & Navigation | 57 | Included |
| F02-002 | Home Page | 31 | Included |
| F02-003 | Company & Service Content Pages | 35 | Included |
| F02-004 | Contact & Enquiry Form | 45 | Included |
| F02-005 | Existing Content Migration | 15 | Included |
|  | Module total | 183 |  |

## 03. Product Catalogue Pages

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F03-001 | Mouldings Landing Page | 21 | Included |
| F03-002 | Category Listing Page with Filters | 59 | Included |
| F03-003 | Product Detail Page | 49 | Included |
| F03-004 | Catalogue Search | 31 | Included |
| F03-005 | Product Enquiry | 17 | Included |
| F03-006 | Combinations Pages | 29 | Optional |
|  | Module total | 206 |  |

## 04. One-time Product Data Migration

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F04-001 | Source Catalogue Extraction Utility | 65 | Included |
| F04-002 | Product Image Acquisition & Optimisation | 28 | Included |
| F04-003 | Data Normalisation & Validation | 53 | Included |
| F04-004 | Garrison Review Workbook & Sign-off | 27 | Included |
| F04-005 | Catalogue Data Build & Publishing | 31 | Included |
| F04-006 | Interior Doors & In-Stock Product Extension | 41 | Optional |
|  | Module total | 245 |  |

## 05. Hosting, SEO & Launch

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F05-001 | SEO Foundation & Redirects | 29 | Included |
| F05-002 | Hosting, Domain, SSL & DNS Cutover | 41 | Included |
| F05-003 | Analytics & Cookie Consent | 17 | Included |
| F05-004 | Quality Assurance, Accessibility & Performance | 34 | Included |
| F05-005 | UAT, Launch & Handover | 28 | Included |
|  | Module total | 149 |  |

# 5. Volumes and Rates

201 moulding products were confirmed in 21 categories of the source catalogue; the remaining categories are counted at project start. The estimate uses 350 products and about 15 existing website pages.

| Item | Basis |
| --- | --- |
| Per-product data verification | 0.25 hours × 350 |
| Existing page content migration | 1.5 hours × 15 |
| Additional products or pages | Same rates per item |
| Manual capture if automated extraction is not possible | 0.75 hours per product |

# 6. Content Rights and Legal Considerations

Brenlo's product data, codes and photographs belong to Brenlo. Garrison should hold written permission from Brenlo (for example as an authorised dealer) before they are published. This is a go/no-go condition.

# 7. Indicative Delivery Phasing

Discovery and design: content capture, wireframes, visual design approval.

Build: website foundation, pages, content migration and catalogue pages.

Product set-up: extraction, preparation, images, Garrison review and sign-off.

Launch: testing, user acceptance testing, domain switch-over and handover.

Indicative duration: About 9 weeks with 3 people, or 7 weeks with 4, subject to timely approvals and access.

# 8. Items Not Included

Administration portal, user roles and publishing workflow

New logo or brand identity, copywriting and photography

New product descriptions, technical drawings or documents

E-commerce, pricing or quoting

Hosting, domain and third-party service fees

Obtaining permission from Brenlo, and legal advice

Project management (quoted separately if required)

# 9. Key Assumptions and Dependencies

Garrison provides domain/registrar access; the current website's source code is not required.

Company email on Google Workspace continues to work; its records are preserved at switch-over.

Planning quantities of 350 products and 15 pages; variance at the stated rates.

Garrison supplies brand assets and approves content, designs and the product list within two review rounds each.

Products change rarely; later changes are made by a developer.

# 10. Comparison of the Three Options

|  | Option 1: Design + Migration | Option 2: + AI Images | Option 3: Premium Platform |
| --- | --- | --- | --- |
| Software effort (go-live features) | 862 | 1078 | 4057 |
| Volume-based effort (products, pages, images) | 111 | 286 | Population by Garrison via admin portal |
| Total go-live effort (hours) | 973 | 1364 | 4057 |
| Optional features (hours) | 70 | 91 | 68 |
| AI service fees (pass-through) | — | USD 162–532 (cap USD 600) | — |
| New website design included | Yes | Yes | No (design phase excluded from estimate) |
| Admin portal and roles | No | No | Yes |
| Product images | Source images (permission needed) | Original AI-assisted images | Source or Garrison images, rights tracked |
| Later product changes | Developer | Developer | Garrison self-service |
| Indicative duration | About 9 weeks with 3 people, or 7 weeks with 4 | About 12 weeks with 3 people, or 9 weeks with 4 | 17–20 weeks (5–6 people) |

# 11. Disclaimer

Estimates are indicative. Final effort depends on the confirmed product and page counts, approval turnaround and access to the source catalogue.