Effort Estimate

Garrison Website Design, Product Catalogue Migration & AI Product Imagery (Option 2)

Prepared for Garrison Industries · Effort in person-hours

Date: 2026-10-07 · Project code: GWA

# 1. Introduction

This document estimates the effort to redesign the Garrison website (www.garrisonindustries.ky) and publish the moulding products from the Brenlo online catalogue on it, with original AI-assisted product images.

Garrison has advised that products change rarely, so catalogue set-up (categories, styles, products and reference data) is done once and no administration portal is included. Garrison approves the product list through a review workbook; later changes are made by a developer. Because the current website's source code and admin logins are not available, the website is rebuilt from its public content in a new design; only domain access is needed.

Product images are not copied from the source catalogue. Each product's outline is drawn to its published dimensions, rendered in 3D, and finished with an AI image service for a realistic look. Lifestyle images for the home page and category banners are also generated.

# 2. Summary Totals

| Bucket | Person-hours |
| --- | --- |
| Software and design (included features) | 1078 |
| Per-product data verification (350 × 0.25 h) | 88 |
| Existing page content migration (15 × 1.5 h) | 23 |
| Profile silhouette preparation (operator time) (350 × 0.3 h) | 105 |
| AI image review and selection (350 × 0.2 h) | 70 |
| Recommended total | 1364 |
| Optional features | 91 |

# 3. AI Service Cost (separate from effort)

AI image service fees are a pass-through cost paid at provider rates, shown separately from effort. Estimates use current list prices for a leading commercial image model and include image inputs.

| Item | Generations |
| --- | --- |
| Style exploration and 20-product pilot | 200 |
| Product images (350 products × about 4 candidates incl. regenerations) | 1400 |
| Lifestyle and category scenes (about 25 scenes × 10 candidates) | 250 |
| Total | 1850 |

| Price basis | Fees (USD) | With 25% contingency (USD) |
| --- | --- | --- |
| Standard quality (about USD 0.07 per image) | 130 | 162 |
| High quality (about USD 0.23 per image) | 426 | 532 |

Recommended budget cap: USD 600, enforced as a spending limit on the AI account. Optional finish variants (up to three per product) add about USD 147–483. Enterprise services with output indemnity are priced by provider quote.

# 4. Module-wise Summary

| Module | Features | Hours |
| --- | --- | --- |
| 01. Discovery & Website Design | 3 | 149 |
| 02. Website Build | 5 | 183 |
| 03. Product Catalogue Pages | 6 | 206 |
| 04. One-time Product Data Migration | 6 | 231 |
| 05. Hosting, SEO & Launch | 5 | 149 |
| 06. AI Product Imagery | 7 | 251 |
| Software total | 32 | 1169 |

# 5. Feature-wise Detail

## 01. Discovery & Website Design

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F01-001 | Existing Website Discovery & Content Capture | 34 | Included |
| F01-002 | Information Architecture & Wireframes | 36 | Included |
| F01-003 | Visual Design System & Page Designs | 79 | Included |
|  | Module total | 149 |  |

## 02. Website Build

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F02-001 | Site Foundation, Layout & Navigation | 57 | Included |
| F02-002 | Home Page | 31 | Included |
| F02-003 | Company & Service Content Pages | 35 | Included |
| F02-004 | Contact & Enquiry Form | 45 | Included |
| F02-005 | Existing Content Migration | 15 | Included |
|  | Module total | 183 |  |

## 03. Product Catalogue Pages

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F03-001 | Mouldings Landing Page | 21 | Included |
| F03-002 | Category Listing Page with Filters | 59 | Included |
| F03-003 | Product Detail Page | 49 | Included |
| F03-004 | Catalogue Search | 31 | Included |
| F03-005 | Product Enquiry | 17 | Included |
| F03-006 | Combinations Pages | 29 | Optional |
|  | Module total | 206 |  |

## 04. One-time Product Data Migration

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F04-001 | Source Catalogue Extraction Utility | 65 | Included |
| F04-002 | Reference Image Capture (Internal Use Only) | 14 | Included |
| F04-003 | Data Normalisation & Validation | 53 | Included |
| F04-004 | Garrison Review Workbook & Sign-off | 27 | Included |
| F04-005 | Catalogue Data Build & Publishing | 31 | Included |
| F04-006 | Interior Doors & In-Stock Product Extension | 41 | Optional |
|  | Module total | 231 |  |

## 05. Hosting, SEO & Launch

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F05-001 | SEO Foundation & Redirects | 29 | Included |
| F05-002 | Hosting, Domain, SSL & DNS Cutover | 41 | Included |
| F05-003 | Analytics & Cookie Consent | 17 | Included |
| F05-004 | Quality Assurance, Accessibility & Performance | 34 | Included |
| F05-005 | UAT, Launch & Handover | 28 | Included |
|  | Module total | 149 |  |

## 06. AI Product Imagery

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F06-001 | AI Imagery Style Guide, Model Setup & Pilot | 47 | Included |
| F06-002 | Profile Silhouette Preparation | 35 | Included |
| F06-003 | Base Render & AI Image Generation | 60 | Included |
| F06-004 | Image Review, Selection & Touch-up | 42 | Included |
| F06-005 | Lifestyle & Category Hero Images | 31 | Included |
| F06-006 | AI Image Disclosure & Provenance Record | 15 | Included |
| F06-007 | Finish / Species Variant Images | 21 | Optional |
|  | Module total | 251 |  |

# 6. Volumes and Rates

201 moulding products were confirmed in 21 categories of the source catalogue; the remaining categories are counted at project start. The estimate uses 350 products and about 15 existing website pages.

| Item | Basis |
| --- | --- |
| Per-product data verification | 0.25 hours × 350 |
| Existing page content migration | 1.5 hours × 15 |
| Profile silhouette preparation (operator time) | 0.3 hours × 350 |
| AI image review and selection | 0.2 hours × 350 |
| Additional products or pages | Same rates per item |
| Manual capture if automated extraction is not possible | 0.75 hours per product |

# 7. Content Rights and Legal Considerations

Brenlo's product data, codes and photographs belong to Brenlo. Garrison should hold written permission from Brenlo (for example as an authorised dealer) before they are published. This is a go/no-go condition.

AI-assisted images reduce, but do not remove, the legal risk. Brenlo photographs are not published or given to the AI service, but the profile shapes are still Brenlo's designs unless Garrison provides its own drawings or samples, and the product data still needs permission.

Images are labelled as illustrative and checked against dimension-accurate outlines, so visitors are not misled about the product.

Purely AI-generated images may not be protected by copyright in some jurisdictions, so Garrison may not be able to stop others reusing them.

Only AI services licensed for commercial use will be used. Some providers offer output indemnity under enterprise plans, usually excluding outputs based on image inputs that themselves infringe; our approach sends only our own renders and text prompts.

We recommend Garrison's legal counsel reviews this approach before go-live. This document is not legal advice.

# 8. Indicative Delivery Phasing

Discovery and design: content capture, wireframes, visual design approval.

Build: website foundation, pages, content migration and catalogue pages.

Product set-up: extraction, preparation, product outlines, image pilot and AI image generation, Garrison review and sign-off.

Launch: testing, user acceptance testing, domain switch-over and handover.

Indicative duration: About 12 weeks with 3 people, or 9 weeks with 4, subject to timely approvals and access.

# 9. Items Not Included

Administration portal, user roles and publishing workflow

New logo or brand identity, copywriting and photography

New product descriptions, technical drawings or documents

E-commerce, pricing or quoting

Hosting, domain and third-party service fees (AI fees are listed separately above)

Obtaining permission from Brenlo, and legal advice

Project management (quoted separately if required)

# 10. Key Assumptions and Dependencies

Garrison provides domain/registrar access; the current website's source code is not required.

Company email on Google Workspace continues to work; its records are preserved at switch-over.

Planning quantities of 350 products and 15 pages; variance at the stated rates.

Garrison supplies brand assets and approves content, designs and the product list within two review rounds each.

Products change rarely; later changes are made by a developer.

AI service fees are paid at cost within the agreed cap.

Garrison's counsel reviews the AI imagery approach before go-live.

# 11. Comparison of the Three Options

|  | Option 1: Design + Migration | Option 2: + AI Images | Option 3: Premium Platform |
| --- | --- | --- | --- |
| Software effort (go-live features) | 862 | 1078 | 4057 |
| Volume-based effort (products, pages, images) | 111 | 286 | Population by Garrison via admin portal |
| Total go-live effort (hours) | 973 | 1364 | 4057 |
| Optional features (hours) | 70 | 91 | 68 |
| AI service fees (pass-through) | — | USD 162–532 (cap USD 600) | — |
| New website design included | Yes | Yes | No (design phase excluded from estimate) |
| Admin portal and roles | No | No | Yes |
| Product images | Source images (permission needed) | Original AI-assisted images | Source or Garrison images, rights tracked |
| Later product changes | Developer | Developer | Garrison self-service |
| Indicative duration | About 9 weeks with 3 people, or 7 weeks with 4 | About 12 weeks with 3 people, or 9 weeks with 4 | 17–20 weeks (5–6 people) |

# 12. Disclaimer

Estimates are indicative. Final effort depends on the confirmed product and page counts, approval turnaround and access to the source catalogue, and AI service pricing at the time of generation.