Product Migration Effort Estimate

Garrison Catalogue Product Migration to Existing Website

Prepared for Garrison Industries · Option B · Effort in person-hours

Date: 2026-10-06 · Project code: GPM

# 1. Introduction

This document estimates the effort to move the moulding products shown in the Brenlo online catalogue onto the existing Garrison website (www.garrisonindustries.ky). The products are extracted, prepared and reviewed by Garrison, then published as catalogue pages within the current website and theme: a mouldings landing page, category listings with filters, product pages, search and a product enquiry link.

This option has no administration portal. After go-live, product changes are made by a developer updating the prepared dataset and reloading it. For Garrison self-service maintenance, see Option A (full catalogue platform).

# 2. Summary Totals

| Bucket | Person-hours |
| --- | --- |
| Software (go-live features) | 536 |
| Per-product verification (350 products) | 88 |
| Recommended total | 624 |
| Optional features | 70 |

# 3. Module-wise Summary

| Module | Features | Hours |
| --- | --- | --- |
| 01. Catalogue Data Extraction & Preparation | 5 | 214 |
| 02. Product Data Store on Existing Website | 2 | 62 |
| 03. Catalogue Pages on Existing Website | 6 | 208 |
| 04. Website Integration, SEO & Go-live | 4 | 122 |
| Software total | 17 | 606 |

# 4. Feature-wise Detail

## 01. Catalogue Data Extraction & Preparation

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F01-001 | Source Catalogue Extraction Utility | 65 | Included |
| F01-002 | Product Image Acquisition & Optimisation | 28 | Included |
| F01-003 | Data Normalisation & Validation | 53 | Included |
| F01-004 | Garrison Review Workbook & Sign-off | 27 | Included |
| F01-005 | Interior Doors & In-Stock Product Extension | 41 | Optional |
|  | Module total | 214 |  |

## 02. Product Data Store on Existing Website

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F02-001 | Product Data Store & Loader | 45 | Included |
| F02-002 | Media Hosting & Delivery Setup | 17 | Included |
|  | Module total | 62 |  |

## 03. Catalogue Pages on Existing Website

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F03-001 | Mouldings Landing Page | 19 | Included |
| F03-002 | Category Listing Page with Filters | 59 | Included |
| F03-003 | Product Detail Page | 47 | Included |
| F03-004 | Catalogue Search | 31 | Included |
| F03-005 | Product Enquiry Handoff | 23 | Included |
| F03-006 | Combinations Pages | 29 | Optional |
|  | Module total | 208 |  |

## 04. Website Integration, SEO & Go-live

| Feature ID | Feature Name | Hours | Notes |
| --- | --- | --- | --- |
| F04-001 | Source Code Onboarding & Environment Setup | 41 | Included |
| F04-002 | Navigation & Theme Integration | 27 | Included |
| F04-003 | SEO, Sitemap & Redirects | 25 | Included |
| F04-004 | Migration Reconciliation & Go-live | 29 | Included |
|  | Module total | 122 |  |

# 5. Product Volume and Rates

The moulding catalogue was reviewed category by category. 201 products were confirmed in 21 categories; the remaining categories will be counted at project start. The estimate uses a planning quantity of 350 products.

| Item | Basis |
| --- | --- |
| Per-product verification (included above) | 0.25 hours per product × 350 products |
| Additional products beyond the planning quantity | 0.25 hours per product |
| Manual capture, if automated extraction is not possible | 0.75 hours per product |
| Optional doors and sheet goods products | 0.25 hours per product, plus the optional feature hours |

# 6. Indicative Delivery Phasing

Onboarding: source code and access, technical assessment, staging environment and backup.

Data preparation: extraction, image optimisation, normalisation and Garrison review workbook.

Website build: product data store, catalogue pages, navigation, theme and SEO.

Go-live: reconciliation, user acceptance testing, production deployment and handover.

Indicative duration: 7–8 weeks with two developers, or about 5 weeks with three, subject to timely access and review.

# 7. Items Not Included

Administration portal, user roles and publishing workflow

Writing new product descriptions, technical drawings or documents

Website redesign, hosting migration or SSL certificate remediation

E-commerce, pricing or quoting

Obtaining permission from Brenlo to reproduce product data and images

# 8. Key Assumptions and Dependencies

Garrison holds written permission from Brenlo to reproduce its product data and images on the Garrison website before go-live.

Garrison owns and provides the complete, current source code of its website (including themes, plugins and database), with the right to modify it, plus server, database and hosting access. If the source code is not available, this estimate does not apply and will be revised.

The existing website technology can host new page templates and product data.

The source catalogue remains accessible for automated extraction; otherwise a supplier data file or the manual capture rate applies.

Product pages show the information available in the source catalogue: code, category, style, dimensions, species and image.

Enquiries use the existing Garrison contact form or email.

Garrison completes the product review within two review rounds.

# 9. Disclaimer

Estimates are indicative. Final effort depends on the existing website technology, the confirmed product count and the accessibility of the source catalogue.